## Report
|  |  |  | CONTRACT PERFORMANCE REPORT | [8 empty] | FORM APPROVED
|  |  |  | FORMAT 1 - WORK BREAKDOWN STRUCTURE | [7 empty] | Dollars | OMB No. 0704-0188 (modified)
1. CONTRACTOR |  |  |  | 2. CONTRACT |  |  |  |  | 3. PROGRAM |  |  | 4. REPORT PERIOD
a. NAME |  |  |  | a. NAME |  |  |  |  | a. NAME |  |  | a. FROM (YYYYMMDD) |  | 2016-04-01
[9 empty] | Cryogenics AIP |  |  | b. TO (YYYYMMDD) |  | 2016-04-30
5. CONTRACT DATA
a. QUANTITY | b. NEGOTIATED | c. ESTIMATED COST OF |  | d. TARGET PROFIT/FEE |  | e. TARGET PRICE |  | f. ESTIMATED PRICE |  | g. CONTRACT CEILING |  | i. DATE OF OTB/OTS (YYYYMMDD)
| COST | AUTHORIZED UNPRICED WORK
1 | 9545352 | 0 |  | 0 |  | 9545352 |  | 9545352 |  | 9545352
6. ESTIMATED COST AT COMPLETION | [7 empty] | 7. SCHED PERFORM INDEX/COST PERFORM INDEX |  |  |  | 8. CONTINGENCY (on remaining)
|  | MANAGEMENT ESTIMATE |  | CONTRACT BUDGET |  | VARIANCE |  | SPI = | 0.92139
|  | AT COMPLETION |  | BASE |  |  |  | CPI = | 0.98927 |  |  | Cont % = | 35.32%
|  | 8572684.2899 |  | 8511149.226 |  | -61535.0639 | [5 empty] | (Factors in VAC)
9. PERFORMANCE DATA
Control Account.WBS (1) |  | CURRENT PERIOD |  |  |  |  | CUMULATIVE TO DATE |  |  |  |  | AT COMPLETION
Control Account.WBS (2) |  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED | ESTIMATED | VARIANCE
Control Account.WBS (3) |  | WORK | WORK | COST WORK |  |  | WORK | WORK | COST WORK
Control Account.WBS (4) |  | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST
(1) |  | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (14) | (15) | (16)
Cryo1 Muon Campus Cryo - AIP |  | 145042.4723 | 47193.9024 | 110927.35 | -97848.5699 | -63733.4476 | 6248132.8887 | 5756936.9348 | 5819386.84 | -491195.9539 | -62449.9052 | 8511149.226 | 8572684.2899 | -61535.0639
Cryo1.02 Cryo Proj Mgmt |  | 14555.4213 | 14555.4213 | 7043.52 | 0 | 7511.9013 | 395218.0059 | 395218.0059 | 240433.9 | 0 | 154784.1059 | 636011.69 | 470729.0386 | 165282.6514
Cryo1.02.01 Gen Proj OS |  | 14555.4213 | 14555.4213 | 7043.52 | 0 | 7511.9013 | 395218.0059 | 395218.0059 | 240433.9 | 0 | 154784.1059 | 636011.69 | 470729.0386 | 165282.6514
Cryo1.02.01.01 Cryo AIP Gen Proj OS - FY13 |  | 0 | 0 | 0 | 0 | 0 | 51346.4223 | 51346.4223 | 43241.15 | 0 | 8105.2723 | 51346.4223 | 43241.15 | 8105.2723
Cryo1.02.01.02 Cryo AIP Gen Proj OS - FY14 |  | 0 | 0 | 0 | 0 | 0 | 133151.102 | 133151.102 | 75120.23 | 0 | 58030.872 | 133151.102 | 75120.23 | 58030.872
Cryo1.02.01.03 Cryo AIP Gen Proj OS - FY15 |  | 0 | 0 | 0 | 0 | 0 | 32348.8042 | 32348.8042 | 38466.11 | 0 | -6117.3058 | 32348.8042 | 38466.11 | -6117.3058
Cryo1.02.01.04 Cryo AIP Gen Proj OS - FY16 |  | 14555.4213 | 14555.4213 | 7043.52 | 0 | 7511.9013 | 104322.6434 | 104322.6434 | 51963.51 | 0 | 52359.1334 | 174327.2891 | 121968.1557 | 52359.1334
Cryo1.02.01.05 Cryo AIP Gen Proj OS - FY17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170789.0384 | 160290.4929 | 10498.5455
Cryo1.02.01.07 Cryo AIP Gen Proj OS - FY15 Supp |  | 0 | 0 | 0 | 0 | 0 | 74049.034 | 74049.034 | 31642.9 | 0 | 42406.134 | 74049.034 | 31642.9 | 42406.134
Cryo1.03 Cryo Basic Engineering |  | 0 | 0 | 0 | 0 | 0 | 269176.6581 | 269176.6581 | 341913.16 | 0 | -72736.5019 | 269176.6581 | 341913.16 | -72736.5019
Cryo1.03 Cryo Basic Engineering |  | 0 | 0 | 0 | 0 | 0 | 269176.6581 | 269176.6581 | 341913.16 | 0 | -72736.5019 | 269176.6581 | 341913.16 | -72736.5019
Cryo1.03 Cryo Basic Engineering |  | 0 | 0 | 0 | 0 | 0 | 269176.6581 | 269176.6581 | 341913.16 | 0 | -72736.5019 | 269176.6581 | 341913.16 | -72736.5019
Cryo1.04 Cryogenic plant sub systems |  | 0 | 0 | 0 | 0 | 0 | 3727547.1192 | 3727547.1192 | 3944618.51 | 0 | -217071.3908 | 3727547.1192 | 3944618.51 | -217071.3908
Cryo1.04.01 LN2 system |  | 0 | 0 | 0 | 0 | 0 | 413528.8731 | 413528.8731 | 331492.16 | 0 | 82036.7131 | 413528.8731 | 331492.16 | 82036.7131
Cryo1.04.01 LN2 system |  | 0 | 0 | 0 | 0 | 0 | 413528.8731 | 413528.8731 | 331492.16 | 0 | 82036.7131 | 413528.8731 | 331492.16 | 82036.7131
Cryo1.04.02 Gas management system |  | 0 | 0 | 0 | 0 | 0 | 236065.7847 | 236065.7847 | 208201.27 | 0 | 27864.5147 | 236065.7847 | 208201.27 | 27864.5147
Cryo1.04.02 Gas management system |  | 0 | 0 | 0 | 0 | 0 | 236065.7847 | 236065.7847 | 208201.27 | 0 | 27864.5147 | 236065.7847 | 208201.27 | 27864.5147
Cryo1.04.03 ODH system |  | 0 | 0 | 0 | 0 | 0 | 49757.6345 | 49757.6345 | 41355.8 | 0 | 8401.8345 | 49757.6345 | 41355.8 | 8401.8345
Cryo1.04.03 ODH system |  | 0 | 0 | 0 | 0 | 0 | 49757.6345 | 49757.6345 | 41355.8 | 0 | 8401.8345 | 49757.6345 | 41355.8 | 8401.8345
Cryo1.04.04 Cryo Refrigerator system |  | 0 | 0 | 0 | 0 | 0 | 1435657.1292 | 1435657.1292 | 1750865.6 | 0 | -315208.4708 | 1435657.1292 | 1750865.6 | -315208.4708
Cryo1.04.04 Cryo Refrigerator system |  | 0 | 0 | 0 | 0 | 0 | 1435657.1292 | 1435657.1292 | 1750865.6 | 0 | -315208.4708 | 1435657.1292 | 1750865.6 | -315208.4708
Cryo1.04.05 Cryo Compressor System |  | 0 | 0 | 0 | 0 | 0 | 426592.2083 | 426592.2083 | 417384.14 | 0 | 9208.0683 | 426592.2083 | 417384.14 | 9208.0683
Cryo1.04.05 Cryo Compressor System |  | 0 | 0 | 0 | 0 | 0 | 426592.2083 | 426592.2083 | 417384.14 | 0 | 9208.0683 | 426592.2083 | 417384.14 | 9208.0683
Cryo1.04.06 Cryo Interconnect Piping |  | 0 | 0 | 0 | 0 | 0 | 737933.9081 | 737933.9081 | 577317.18 | 0 | 160616.7281 | 737933.9081 | 577317.18 | 160616.7281
Cryo1.04.06 Cryo Interconnect Piping |  | 0 | 0 | 0 | 0 | 0 | 737933.9081 | 737933.9081 | 577317.18 | 0 | 160616.7281 | 737933.9081 | 577317.18 | 160616.7281
Cryo1.04.07 Cryo Interconnect Electrical & Controls |  | 0 | 0 | 0 | 0 | 0 | 166153.655 | 166153.655 | 270568.41 | 0 | -104414.755 | 166153.655 | 270568.41 | -104414.755
Cryo1.04.07 Cryo Interconnect Electrical & Controls |  | 0 | 0 | 0 | 0 | 0 | 166153.655 | 166153.655 | 270568.41 | 0 | -104414.755 | 166153.655 | 270568.41 | -104414.755
Cryo1.04.08 Cryogenic Fluids |  | 0 | 0 | 0 | 0 | 0 | 261857.9263 | 261857.9263 | 347433.95 | 0 | -85576.0237 | 261857.9263 | 347433.95 | -85576.0237
Cryo1.04.08 Cryogenic Fluids |  | 0 | 0 | 0 | 0 | 0 | 261857.9263 | 261857.9263 | 347433.95 | 0 | -85576.0237 | 261857.9263 | 347433.95 | -85576.0237
Cryo1.05 Experiment interfaces |  | 56620.622 | 29519.4678 | 86162.07 | -27101.1542 | -56642.6022 | 784265.4233 | 604430.3043 | 572645.59 | -179835.119 | 31784.7143 | 1135253.9216 | 1108927.3879 | 26326.5337
Cryo1.05.01 Mu2e Interface Connection |  | 56620.622 | 29519.4678 | 86162.07 | -27101.1542 | -56642.6022 | 757066.4993 | 577231.3803 | 547479.19 | -179835.119 | 29752.1903 | 1108054.9976 | 1083760.9879 | 24294.0097
Cryo1.05.01 Mu2e Interface Connection |  | 56620.622 | 29519.4678 | 86162.07 | -27101.1542 | -56642.6022 | 757066.4993 | 577231.3803 | 547479.19 | -179835.119 | 29752.1903 | 1108054.9976 | 1083760.9879 | 24294.0097
Cryo1.05.02 g-2 interface connection |  | 0 | 0 | 0 | 0 | 0 | 27198.924 | 27198.924 | 25166.4 | 0 | 2032.524 | 27198.924 | 25166.4 | 2032.524
Cryo1.05.02 g-2 interface connection |  | 0 | 0 | 0 | 0 | 0 | 27198.924 | 27198.924 | 25166.4 | 0 | 2032.524 | 27198.924 | 25166.4 | 2032.524
Cryo1.06 Cryo Safety Documents |  | 0 | 0 | 0 | 0 | 0 | 155311.4174 | 155311.4174 | 125539.02 | 0 | 29772.3974 | 155311.4174 | 125539.02 | 29772.3974
Cryo1.06 Cryo Safety Documents |  | 0 | 0 | 0 | 0 | 0 | 155311.4174 | 155311.4174 | 125539.02 | 0 | 29772.3974 | 155311.4174 | 125539.02 | 29772.3974
Cryo1.06 Cryo Safety Documents |  | 0 | 0 | 0 | 0 | 0 | 155311.4174 | 155311.4174 | 125539.02 | 0 | 29772.3974 | 155311.4174 | 125539.02 | 29772.3974
Cryo1.07 Testing/Checkout |  | 0 | 0 | 0 | 0 | 0 | 65416.1207 | 65416.1207 | 233.53 | 0 | 65182.5907 | 135458.102 | 69768.2495 | 65689.8525
Cryo1.07 Testing/Checkout |  | 0 | 0 | 0 | 0 | 0 | 65416.1207 | 65416.1207 | 233.53 | 0 | 65182.5907 | 135458.102 | 69768.2495 | 65689.8525
Cryo1.07 Testing/Checkout |  | 0 | 0 | 0 | 0 | 0 | 65416.1207 | 65416.1207 | 233.53 | 0 | 65182.5907 | 135458.102 | 69768.2495 | 65689.8525
Cryo1.08 Cryo g-2 Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 114470.8338 | 114470.8338 | 55084.2 | 0 | 59386.6338 | 114470.8338 | 55084.2 | 59386.6338
Cryo1.08 Cryo g-2 Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 114470.8338 | 114470.8338 | 55084.2 | 0 | 59386.6338 | 114470.8338 | 55084.2 | 59386.6338
Cryo1.08 Cryo g-2 Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 114470.8338 | 114470.8338 | 55084.2 | 0 | 59386.6338 | 114470.8338 | 55084.2 | 59386.6338
Cryo1.09 Cryo Mu2e Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97077.9555 | 97719.3744 | -641.4189
Cryo1.09 Cryo Mu2e Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97077.9555 | 97719.3744 | -641.4189
Cryo1.09 Cryo Mu2e Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97077.9555 | 97719.3744 | -641.4189
Cryo1.10 Cryo Distribution Box (CDB) |  | 73866.429 | 3119.0133 | 17721.76 | -70747.4157 | -14602.7467 | 736727.3103 | 425366.4754 | 538918.93 | -311360.8349 | -113552.4546 | 2240841.5284 | 2358385.3495 | -117543.8211
Cryo1.10 Cryo Distribution Box (CDB) |  | 73866.429 | 3119.0133 | 17721.76 | -70747.4157 | -14602.7467 | 736727.3103 | 425366.4754 | 538918.93 | -311360.8349 | -113552.4546 | 2240841.5284 | 2358385.3495 | -117543.8211
Cryo1.10 Cryo Distribution Box (CDB) |  | 73866.429 | 3119.0133 | 17721.76 | -70747.4157 | -14602.7467 | 736727.3103 | 425366.4754 | 538918.93 | -311360.8349 | -113552.4546 | 2240841.5284 | 2358385.3495 | -117543.8211
a. SUBTOTAL |  | 145042.4723 | 47193.9024 | 110927.35 | -97848.5699 | -63733.4476 | 6248132.8887 | 5756936.9348 | 5819386.84 | -491195.9539 | -62449.9052 | 8511149.236 | 8572684.2899 | -61535.0539
b. MANAGEMENT RESERVE | [11 empty] | 1034202.77
c. TOTAL |  | 145042.4723 | 47193.9024 | 110927.35 | -97848.5699 | -63733.4476 | 6248132.8887 | 5756936.9348 | 5819386.84 | -491195.9539 | -62449.9052 | 9545352.006

## Template
<Header>{Report} | [7 empty] | {CostProject.Classification}
<Header>{Report} | CLASSIFICATION (When Filled In)
<Header>{Report} |  |  |  |  | CONTRACT PERFORMANCE REPORT | [13 empty] | FORM APPROVED
<Header>{Report} |  |  |  |  | FORMAT 1 - WORK BREAKDOWN STRUCTURE | [11 empty] | DOLLARS IN | {ReportSetting.ScaleCaption} | OMB No. 0704-0188
<Header>{Report} | 1. CONTRACTOR |  |  |  | 2. CONTRACT |  |  |  |  | 3. PROGRAM | [7 empty] | 4. REPORT PERIOD
<Header>{Report} | a. NAME |  |  |  | a. NAME |  |  |  |  | a. NAME | [7 empty] | a. FROM (YYYYMMDD)
<Header>{Report} | {CostProject.ContractorName} |  |  |  | {CostProject.ContractName} |  |  |  |  | {CostProject.Description}
<Header>{Report} | b. LOCATION (Address and ZIP Code) |  |  |  | b. NUMBER |  |  |  |  | b. PHASE | [7 empty] | {CostProject.PeriodStartDate}{NoCellFormat}
<Header>{Report} | {CostProject.ContractorLocation} |  |  |  | {CostProject.ContractNumber} |  |  |  |  | {CostProject.ContractPhase} | [7 empty] | b. TO (YYYYMMDD)
<Header>{Report} |  |  |  |  | c. TYPE |  |  | d. SHARE RATIO |  | c. EVMS ACCEPTANCE
<Header>{Report} |  |  |  |  | {CostProject.ContractType} |  |  | {CostProject.ShareRate} |  | {=if(CostProject.EvmsAcceptance.Id=0,"X"," ")} | NO | {=if(CostProject.EvmsAcceptance.Id=1,"X"," ")} | YES | (YYYYMMDD) | {=IF(OR(CostProject.EvmsAcceptance.Id=0,CostProject.EvmsAcceptance.Id=1), IF(CostProject.EvmsAcceptanceDate=0, " ", CostProject.EvmsAcceptanceDate), IF(CostProject.EvmsAcceptance.Id=2, "N/A"," "))}{NoCellFormat} |  |  | {CostProject.StatusDate}{NoCellFormat}
<Header>{Report} | 5. CONTRACT DATA
<Header>{Report} | a. QUANTITY | b. NEGOTIATED | c. ESTIMATED COST OF |  | d. TARGET PROFIT/FEE |  | e. TARGET PRICE |  | f. ESTIMATED PRICE |  |  | g. CONTRACT CEILING |  |  | h. ESTIMATED CONTRACT CEILING |  |  | i. DATE OF OTB/OTS (YYYYMMDD)
<Header>{Report} |  | COST | AUTHORIZED UNPRICED WORK
<Header>{Report} | {CostProject.Quantity} | {CostProject.Ctc} | {CostProject.Auw} |  | {=CostProject.Ctc*(CostProject.FeePct/100)} |  | {=CostProject.Fee+CostProject.Ctc} |  | {=CostProject.Lre+(CostProject.Cbb*(CostProject.FeePct/100))} |  |  | {CostProject.Ceiling} |  |  | {CostProject.EstCeiling} |  |  | {CostProject.OtbDate}{NoCellFormat}
<Header>{Report} | 6. ESTIMATED COST AT COMPLETION | [7 empty] | 7. AUTHORIZED CONTRACTOR REPRESENTATIVE
<Header>{Report} |  |  | MANAGEMENT ESTIMATE |  | CONTRACT BUDGET |  | VARIANCE |  | a. NAME | (Last, First, Middle Initial) |  |  |  |  | b. TITLE
<Header>{Report} |  |  | AT COMPLETION |  | BASE
<Header>{Report} |  |  | (1) |  | (2) |  | (3) |  | {CostProject.ContractRepName} | [5 empty] | {CostProject.ContractRepTitle}
<Header>{Report} | a. BEST CASE |  | {CostProject.EacBestCase} | [5 empty] | c. SIGNATURE | [8 empty] | d. DATE SIGNED | (YYYYMMDD)
<Header>{Report} | b. WORST CASE |  | {CostProject.EacWorstCase}
<Header>{Report} | c. MOST LIKELY |  | {CostProject.Lre} |  | {CostProject.Cbb} |  | {=Cell[R,C-2]-Cell[R,C-4]}
<Header>{Report} | 8. PERFORMANCE DATA
<Header>{Report} | {CriteriaN.Title}{Down}{Replace} |  | CURRENT PERIOD |  |  |  |  | CUMULATIVE TO DATE | [6 empty] | REPROGRAMMING ADJUSTMENTS |  |  | AT COMPLETION
<Header>{Report} |  |  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED COST |  | ACTUAL |  | VARIANCE | [5 empty] | BUDGETED | ESTIMATED | VARIANCE
<Header>{Report} |  |  | WORK | WORK | COST WORK |  |  | WORK | WORK | COST WORK |  |  |  |  | COST | SCHEDULE
<Header>{Report} | ITEM |  | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST | SCHEDULED | PERFORMED | PERFORMED |  | SCHEDULE |  | COST | VARIANCE | VARIANCE | BUDGET
<Header>{Report} | (1) |  | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) |  | (10) |  | (11) | (12a) | (12b) | (13) | (14) | (15) | (16)
<Header>{CriteriaN} | {=CONCATENATE(REPT(" ",CriteriaN.Level-1),"CriteriaN.Id"," CriteriaN.Description")} |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SortCodeC} | b. COST OF MONEY |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SortCodeG} | c. GENERAL AND ADMINISTRATIVE |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} | d. UNDISTRIBUTED BUDGET | [16 empty] | {CostProject.Ub} | {CostProject.EstUb} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SubTotal} | e. SUBTOTAL |  | {Column.Total} | {Column.Total} | {Column.Total} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {Column.Total} | {Column.Total} | {Column.Total} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {Column.Total} | {Column.Total} | {Column.Total} | {=Column.Total+Cell[R-1,C]} | {=Column.Total+Cell[R-1,C]} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} | f. MANAGEMENT RESERVE | [16 empty] | {CostProject.Mr}
<Footer>{Report} | g. TOTAL |  | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} |  | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C] + Cell[R-1,C]}
<Footer>{Report} | 9. RECONCILIATION TO CONTRACT BUDGET BASELINE
<Footer>{Report} | a. VARIANCE ADJUSTMENT | [10 empty] | {=Cell[R-2,C+4]} |  | {=Cell[R-2,C+1]}
<Footer>{Report} | b. TOTAL CONTRACT VARIANCE | [10 empty] | {=Cell[R-3,C]+Cell[R-1,C]} |  | {=Cell[R-3,C]+Cell[R-1,C]} |  |  |  | {CostProject.Cbb} | {CostProject.Lre} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} |  |  | (7): {CostProject.Classification}
<Footer>{Report} | CLASSIFICATION (When Filled In)
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Report Options
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Criteria: {ReportOptions.Criteria}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Calendar: {ReportOptions.CalendarSet}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Cost Sets: {ReportOptions.CostSets}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Filter: {ReportOptions.Filter}
[18 empty] | $ | % | Both
[18 empty] | Dollar | Percent | Both

## Calendar
Date | 18 Label | Hours
2016-03-31 | PREVIOUS | 15088
2016-04-30 | TODATE | 168
2024-09-30 | ATCOMPLETE | 16944

## Data
Control Account.WBS (1) | Control Account.WBS (2) | Control Account.WBS (3) | Control Account.WBS (4) | Summary Code | Cost Set | Date | Value | Currency
|  |  |  | O | Budget | 2016-03-31 | 2093324.5835 | TRUE
|  |  |  | O | Budget | 2016-04-30 | 36739.8087 | TRUE
|  |  |  | O | Budget | 2024-09-30 | 537115.7539 | TRUE
|  |  |  | O | Earned | 2016-03-31 | 1967255.2617 | TRUE
|  |  |  | O | Earned | 2016-04-30 | 15166.8408 | TRUE
|  |  |  | O | Actuals | 2016-03-31 | 2083218.35 | TRUE
|  |  |  | O | Actuals | 2016-04-30 | 50487.27 | TRUE
|  |  |  | O | EAC | 2016-03-31 | 2083218.35 | TRUE
|  |  |  | O | EAC | 2016-04-30 | 50487.27 | TRUE
|  |  |  | O | EAC | 2024-09-30 | 681590.0106 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.01 |  | Budget | 2016-03-31 | 51346.4223 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.01 |  | Earned | 2016-03-31 | 51346.4223 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.01 |  | Actuals | 2016-03-31 | 43241.15 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.01 |  | EAC | 2016-03-31 | 43241.15 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.02 |  | Budget | 2016-03-31 | 133151.102 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.02 |  | Earned | 2016-03-31 | 133151.102 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.02 |  | Actuals | 2016-03-31 | 75120.23 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.02 |  | EAC | 2016-03-31 | 75120.23 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.03 |  | Budget | 2016-03-31 | 32348.8042 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.03 |  | Earned | 2016-03-31 | 32348.8042 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.03 |  | Actuals | 2016-03-31 | 38466.11 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.03 |  | EAC | 2016-03-31 | 38466.11 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.04 |  | Budget | 2016-03-31 | 89767.2221 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.04 |  | Budget | 2016-04-30 | 14555.4213 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.04 |  | Budget | 2024-09-30 | 70004.6457 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.04 |  | Earned | 2016-03-31 | 89767.2221 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.04 |  | Earned | 2016-04-30 | 14555.4213 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.04 |  | Actuals | 2016-03-31 | 44919.99 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.04 |  | Actuals | 2016-04-30 | 7043.52 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.04 |  | EAC | 2016-03-31 | 44919.99 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.04 |  | EAC | 2016-04-30 | 7043.52 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.04 |  | EAC | 2024-09-30 | 70004.6457 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.05 |  | Budget | 2024-09-30 | 170789.0384 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.05 |  | EAC | 2024-09-30 | 160290.4929 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.07 |  | Budget | 2016-03-31 | 74049.034 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.07 |  | Earned | 2016-03-31 | 74049.034 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.07 |  | Actuals | 2016-03-31 | 31642.9 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.07 |  | EAC | 2016-03-31 | 31642.9 | TRUE
Cryo1 | Cryo1.03 | Cryo1.03 | Cryo1.03 |  | Budget | 2016-03-31 | 269176.6581 | TRUE
Cryo1 | Cryo1.03 | Cryo1.03 | Cryo1.03 |  | Earned | 2016-03-31 | 269176.6581 | TRUE
Cryo1 | Cryo1.03 | Cryo1.03 | Cryo1.03 |  | Actuals | 2016-03-31 | 341913.16 | TRUE
Cryo1 | Cryo1.03 | Cryo1.03 | Cryo1.03 |  | EAC | 2016-03-31 | 341913.16 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.01 | Cryo1.04.01 |  | Budget | 2016-03-31 | 413528.8731 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.01 | Cryo1.04.01 |  | Earned | 2016-03-31 | 413528.8731 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.01 | Cryo1.04.01 |  | Actuals | 2016-03-31 | 331492.16 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.01 | Cryo1.04.01 |  | EAC | 2016-03-31 | 331492.16 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.02 | Cryo1.04.02 |  | Budget | 2016-03-31 | 236065.7847 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.02 | Cryo1.04.02 |  | Earned | 2016-03-31 | 236065.7847 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.02 | Cryo1.04.02 |  | Actuals | 2016-03-31 | 208201.27 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.02 | Cryo1.04.02 |  | EAC | 2016-03-31 | 208201.27 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.03 | Cryo1.04.03 |  | Budget | 2016-03-31 | 49757.6345 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.03 | Cryo1.04.03 |  | Earned | 2016-03-31 | 49757.6345 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.03 | Cryo1.04.03 |  | Actuals | 2016-03-31 | 41355.8 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.03 | Cryo1.04.03 |  | EAC | 2016-03-31 | 41355.8 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.04 | Cryo1.04.04 |  | Budget | 2016-03-31 | 1435657.1292 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.04 | Cryo1.04.04 |  | Earned | 2016-03-31 | 1435657.1292 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.04 | Cryo1.04.04 |  | Actuals | 2016-03-31 | 1750865.6 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.04 | Cryo1.04.04 |  | EAC | 2016-03-31 | 1750865.6 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.05 | Cryo1.04.05 |  | Budget | 2016-03-31 | 426592.2083 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.05 | Cryo1.04.05 |  | Earned | 2016-03-31 | 426592.2083 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.05 | Cryo1.04.05 |  | Actuals | 2016-03-31 | 417384.14 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.05 | Cryo1.04.05 |  | EAC | 2016-03-31 | 417384.14 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.06 | Cryo1.04.06 |  | Budget | 2016-03-31 | 737933.9081 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.06 | Cryo1.04.06 |  | Earned | 2016-03-31 | 737933.9081 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.06 | Cryo1.04.06 |  | Actuals | 2016-03-31 | 577317.18 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.06 | Cryo1.04.06 |  | EAC | 2016-03-31 | 577317.18 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.07 | Cryo1.04.07 |  | Budget | 2016-03-31 | 166153.655 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.07 | Cryo1.04.07 |  | Earned | 2016-03-31 | 166153.655 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.07 | Cryo1.04.07 |  | Actuals | 2016-03-31 | 270568.41 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.07 | Cryo1.04.07 |  | EAC | 2016-03-31 | 270568.41 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.08 | Cryo1.04.08 |  | Budget | 2016-03-31 | 261857.9263 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.08 | Cryo1.04.08 |  | Earned | 2016-03-31 | 261857.9263 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.08 | Cryo1.04.08 |  | Actuals | 2016-03-31 | 347433.95 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.08 | Cryo1.04.08 |  | EAC | 2016-03-31 | 347433.95 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | Budget | 2016-03-31 | 700445.8773 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | Budget | 2016-04-30 | 56620.622 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | Budget | 2024-09-30 | 350988.4983 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | Earned | 2016-03-31 | 547711.9125 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | Earned | 2016-04-30 | 29519.4678 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | Actuals | 2016-03-31 | 461317.12 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | Actuals | 2016-04-30 | 86162.07 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | EAC | 2016-03-31 | 461317.12 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | EAC | 2016-04-30 | 86162.07 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | EAC | 2024-09-30 | 536281.7979 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.02 | Cryo1.05.02 |  | Budget | 2016-03-31 | 27198.924 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.02 | Cryo1.05.02 |  | Earned | 2016-03-31 | 27198.924 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.02 | Cryo1.05.02 |  | Actuals | 2016-03-31 | 25166.4 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.02 | Cryo1.05.02 |  | EAC | 2016-03-31 | 25166.4 | TRUE
Cryo1 | Cryo1.06 | Cryo1.06 | Cryo1.06 |  | Budget | 2016-03-31 | 155311.4174 | TRUE
Cryo1 | Cryo1.06 | Cryo1.06 | Cryo1.06 |  | Earned | 2016-03-31 | 155311.4174 | TRUE
Cryo1 | Cryo1.06 | Cryo1.06 | Cryo1.06 |  | Actuals | 2016-03-31 | 125539.02 | TRUE
Cryo1 | Cryo1.06 | Cryo1.06 | Cryo1.06 |  | EAC | 2016-03-31 | 125539.02 | TRUE
Cryo1 | Cryo1.07 | Cryo1.07 | Cryo1.07 |  | Budget | 2016-03-31 | 65416.1207 | TRUE
Cryo1 | Cryo1.07 | Cryo1.07 | Cryo1.07 |  | Budget | 2024-09-30 | 70041.9813 | TRUE
Cryo1 | Cryo1.07 | Cryo1.07 | Cryo1.07 |  | Earned | 2016-03-31 | 65416.1207 | TRUE
Cryo1 | Cryo1.07 | Cryo1.07 | Cryo1.07 |  | Actuals | 2016-03-31 | 233.53 | TRUE
Cryo1 | Cryo1.07 | Cryo1.07 | Cryo1.07 |  | EAC | 2016-03-31 | 233.53 | TRUE
Cryo1 | Cryo1.07 | Cryo1.07 | Cryo1.07 |  | EAC | 2024-09-30 | 69534.7195 | TRUE
Cryo1 | Cryo1.08 | Cryo1.08 | Cryo1.08 |  | Budget | 2016-03-31 | 114470.8338 | TRUE
Cryo1 | Cryo1.08 | Cryo1.08 | Cryo1.08 |  | Earned | 2016-03-31 | 114470.8338 | TRUE
Cryo1 | Cryo1.08 | Cryo1.08 | Cryo1.08 |  | Actuals | 2016-03-31 | 55084.2 | TRUE
Cryo1 | Cryo1.08 | Cryo1.08 | Cryo1.08 |  | EAC | 2016-03-31 | 55084.2 | TRUE
Cryo1 | Cryo1.09 | Cryo1.09 | Cryo1.09 |  | Budget | 2024-09-30 | 97077.9555 | TRUE
Cryo1 | Cryo1.09 | Cryo1.09 | Cryo1.09 |  | EAC | 2024-09-30 | 97719.3744 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | Budget | 2016-03-31 | 662860.8813 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | Budget | 2016-04-30 | 73866.429 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | Budget | 2024-09-30 | 1504114.2181 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | Earned | 2016-03-31 | 422247.4621 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | Earned | 2016-04-30 | 3119.0133 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | Actuals | 2016-03-31 | 521197.17 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | Actuals | 2016-04-30 | 17721.76 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | EAC | 2016-03-31 | 521197.17 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | EAC | 2016-04-30 | 17721.76 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | EAC | 2024-09-30 | 1819466.4195 | TRUE