## Sheet1
Task Code | CTC | WP | Name | BCWS | BCWP | Schedule Variance
Cryo AIP Total |  |  |  | 7508588 | 6894191 | -614397
A1301.05.01 Mu2e Interface Connection | A1301.05.01 |  | Mu2e Interface Connection | 1095322.05 | 854361.83 | -240960.22
2979 Mu2e Interface - Assemble Other Components | A1301.05.01 | 2979 | Mu2e Interface - Assemble Other Components | 323546.41 | 278249.91 | -45296.5
2980 Mu2e Interface - Assemble/Install Transfer Line | A1301.05.01 | 2980 | Mu2e Interface - Assemble/Install Transfer Line | 209679.52 | 73387.83 | -136291.69
2981 Mu2e Interface - Transfer Line Testing | A1301.05.01 | 2981 | Mu2e Interface - Transfer Line Testing | 52110.42 | 0 | -52110.42
3010 Mu2e Interface - Install Helium Gas Lines between MC-1 and MC-2 | A1301.05.01 | 3010 | Mu2e Interface - Install Helium Gas Lines between MC-1 and MC-2 | 57592.07 | 50330.46 | -7261.61
A1301.10 Cryo Distribution Box (CDB) | A1301.10 |  | Cryo Distribution Box (CDB) | 1427710.44 | 1187742.72 | -239967.72
2955 Fermilab Oversight of CDB | A1301.10 | 2955 | Fermilab Oversight of CDB | 85020.06 | 51751.34 | -33268.72
2964 Procure Transfer line A | A1301.10 | 2964 | Procure Transfer line A | 122728.87 | 36818.66 | -85910.21
2965 TLs from CDB to feedbox | A1301.10 | 2965 | TLs from CDB to feedbox | 155929.07 | 31185.81 | -124743.26
2966 TL from Helium dewar to CDB | A1301.10 | 2966 | TL from Helium dewar to CDB | 0 | 6130.26 | 6130.26
2968 Procure Helium dewar | A1301.10 | 2968 | Procure Helium dewar | 0 | 3065.07 | 3065.07
2993 Procure Heat Exchanger #2 | A1301.10 | 2993 | Procure Heat Exchanger #2 | 34939.07 | 29698.21 | -5240.86
A1301.14 MC-1 Refrigerator Upgrades | A1301.14 |  | MC-1 Refrigerator Upgrades | 155882.14 | 22413.19 | -133468.95
3000 Dampen noisy instrument signals in PLC | A1301.14 | 3000 | Dampen noisy instrument signals in PLC | 6839.39 | 683.94 | -6155.45
3001 Display all Mu2e Refrigerator Variables in iFIX | A1301.14 | 3001 | Display all Mu2e Refrigerator Variables in iFIX | 6009.39 | 5408.45 | -600.94
3002 Calib all Cryo Instrmts, incl Charg VPTs, Trans, Gauges, Check Calib on Thermometry, Flow Meters, etc. | A1301.14 | 3002 | Calib all Cryo Instrmts, incl Charg VPTs, Trans, Gauges, Check Calib on Thermometry, Flow Meters, etc. | 39880.89 | 6722.82 | -33158.07
3003 Inst Press Trace Cables for all Engines, Wired to an Oscill w/Select Switch | A1301.14 | 3003 | Inst Press Trace Cables for all Engines, Wired to an Oscill w/Select Switch | 7386.35 | 738.64 | -6647.71
3004 Correct all Control Loops, Fix Feedback, Retune, 26 Loops for Compressors & One Refrig | A1301.14 | 3004 | Correct all Control Loops, Fix Feedback, Retune, 26 Loops for Compressors & One Refrig | 39997.38 | 0 | -39997.38
3005 Instl Block & Bypass Valves for Purifier, Allow Temp Instl of Mobile Purifier | A1301.14 | 3005 | Instl Block & Bypass Valves for Purifier, Allow Temp Instl of Mobile Purifier | 46336.96 | 3618.7 | -42718.26
3006 Move Nitrogen Gas Pipe | A1301.14 | 3006 | Move Nitrogen Gas Pipe | 3288.52 | 382.76 | -2905.76
3007 Instrument Air Pipeline | A1301.14 | 3007 | Instrument Air Pipeline | 6143.26 | 4857.89 | -1285.37