## Sheet1
Task Code | CTC | WP | Name | BCWS | BCWP | Schedule Variance
Cryo AIP |  |  |  | 8325132 | 7395760 | -929372
A1301.05.01 Mu2e Interface Connection | A1301.05.01 |  | Mu2e Interface Connection | 1190013.59 | 1118078.52 | -71935.07
2979 Mu2e Interface - Assemble Other Components | A1301.05.01 | 2979 | Mu2e Interface - Assemble Other Components | 323546.41 | 300898.16 | -22648.25
2980 Mu2e Interface - Assemble/Install Transfer Line | A1301.05.01 | 2980 | Mu2e Interface - Assemble/Install Transfer Line | 209679.52 | 188711.57 | -20967.95
2981 Mu2e Interface - Transfer Line Testing | A1301.05.01 | 2981 | Mu2e Interface - Transfer Line Testing | 120425.47 | 96314.28 | -24111.19
3010 Mu2e Interface - Install Helium Gas Lines between MC-1 and MC-2 | A1301.05.01 | 3010 | Mu2e Interface - Install Helium Gas Lines between MC-1 and MC-2 | 83968.56 | 79760.88 | -4207.68
A1301.09 Cryo Mu2e Acceptance Tests | A1301.09 |  | Cryo Mu2e Acceptance Tests | 94731 | 0 | -94731
2611 Cryo Mu2e Acceptance Tests | A1301.09 | 2611 | Cryo Mu2e Acceptance Tests | 94731 | 0 | -94731
A1301.10 Cryo Distribution Box (CDB) | A1301.10 |  | Cryo Distribution Box (CDB) | 1867698.02 | 1288938.11 | -578759.91
2955 Fermilab Oversight of CDB | A1301.10 | 2955 | Fermilab Oversight of CDB | 112677.47 | 90551.54 | -22125.93
2964 Procure Transfer line A | A1301.10 | 2964 | Procure Transfer line A | 122728.87 | 36818.66 | -85910.21
2965 TLs from CDB to feedbox | A1301.10 | 2965 | TLs from CDB to feedbox | 155929.07 | 31185.81 | -124743.26
2966 TL from Helium dewar to CDB | A1301.10 | 2966 | TL from Helium dewar to CDB | 27184.67 | 6155.02 | -21029.65
2968 Procure Helium dewar | A1301.10 | 2968 | Procure Helium dewar | 54368.16 | 24619.55 | -29748.61
2997 Vendor Compl Vessel Code Stmp, Theral Shld Compnts, Trace Tube | A1301.10 | 2997 | Vendor Compl Vessel Code Stmp, Theral Shld Compnts, Trace Tube | 189454.87 | 0 | -189454.87
2998 Vendor Compl Piping Spool Subassemblies | A1301.10 | 2998 | Vendor Compl Piping Spool Subassemblies | 89145.67 | 0 | -89145.67
3011 Design Improvements/Upgrades | A1301.10 | 3011 | Design Improvements/Upgrades | 52176.8 | 35575.09 | -16601.71
A1301.14 MC-1 Refrigerator Upgrades | A1301.14 |  | MC-1 Refrigerator Upgrades | 289199.28 | 105253.66 | -183945.62
3000 Dampen noisy instrument signals in PLC | A1301.14 | 3000 | Dampen noisy instrument signals in PLC | 6839.39 | 3419.7 | -3419.69
3002 Calib all Cryo Instrmts, incl Charg VPTs, Trans, Gauges, Check Calib on Thermometry, Flow Meters, etc. | A1301.14 | 3002 | Calib all Cryo Instrmts, incl Charg VPTs, Trans, Gauges, Check Calib on Thermometry, Flow Meters, etc. | 67321.47 | 16807.04 | -50514.43
3003 Inst Press Trace Cables for all Engines, Wired to an Oscill w/Select Switch | A1301.14 | 3003 | Inst Press Trace Cables for all Engines, Wired to an Oscill w/Select Switch | 7386.35 | 738.64 | -6647.71
3004 Correct all Control Loops, Fix Feedback, Retune, 26 Loops for Compressors & One Refrig | A1301.14 | 3004 | Correct all Control Loops, Fix Feedback, Retune, 26 Loops for Compressors & One Refrig | 95089.4 | 4757.44 | -90331.96
3005 Instl Block & Bypass Valves for Purifier, Allow Temp Instl of Mobile Purifier | A1301.14 | 3005 | Instl Block & Bypass Valves for Purifier, Allow Temp Instl of Mobile Purifier | 90725.89 | 58876.83 | -31849.06
3006 Move Nitrogen Gas Pipe | A1301.14 | 3006 | Move Nitrogen Gas Pipe | 7700.47 | 6927.02 | -773.45
3007 Instrument Air Pipeline | A1301.14 | 3007 | Instrument Air Pipeline | 8126.92 | 7717.6 | -409.32