## Report
|  |  |  | CONTRACT PERFORMANCE REPORT | [8 empty] | FORM APPROVED
|  |  |  | FORMAT 1 - WORK BREAKDOWN STRUCTURE | [7 empty] | Dollars | OMB No. 0704-0188 (modified)
1. CONTRACTOR |  |  |  | 2. CONTRACT |  |  |  |  | 3. PROGRAM |  |  | 4. REPORT PERIOD
a. NAME |  |  |  | a. NAME |  |  |  |  | a. NAME |  |  | a. FROM (YYYYMMDD) |  | 2017-04-01
[9 empty] | Cryogenics AIP |  |  | b. TO (YYYYMMDD) |  | 2017-04-30
5. CONTRACT DATA
a. QUANTITY | b. NEGOTIATED | c. ESTIMATED COST OF |  | d. TARGET PROFIT/FEE |  | e. TARGET PRICE |  | f. ESTIMATED PRICE |  | g. CONTRACT CEILING |  | i. DATE OF OTB/OTS (YYYYMMDD)
| COST | AUTHORIZED UNPRICED WORK
1 | 9545352 | 0 |  | 0 |  | 9545352 |  | 9545352 |  | 9545352
6. ESTIMATED COST AT COMPLETION | [7 empty] | 7. SCHED PERFORM INDEX/COST PERFORM INDEX |  |  |  | 8. CONTINGENCY (on remaining)
|  | MANAGEMENT ESTIMATE |  | CONTRACT BUDGET |  | VARIANCE |  | SPI = | 0.92261
|  | AT COMPLETION |  | BASE |  |  |  | CPI = | 0.96726 |  |  | Cont % = | 59.06%
|  | 9113500.5374 |  | 8718662.8777 |  | -394837.6597 | [5 empty] | (Factors in VAC)
9. PERFORMANCE DATA
Control Account.WBS (1) |  | CURRENT PERIOD |  |  |  |  | CUMULATIVE TO DATE |  |  |  |  | AT COMPLETION
Control Account.WBS (2) |  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED | ESTIMATED | VARIANCE
Control Account.WBS (3) |  | WORK | WORK | COST WORK |  |  | WORK | WORK | COST WORK
Control Account.WBS (4) |  | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST
(1) |  | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (14) | (15) | (16)
Cryo1 Muon Campus Cryogenics - AIP |  | 195260.7694 | 119699.2984 | 120511.93 | -75561.471 | -812.6316 | 8657454.4484 | 7987458.6513 | 8257795.4 | -669995.7971 | -270336.7487 | 8718662.8777 | 9113500.5374 | -394837.6597
Cryo1.02 Cryo Proj Mgmt |  | 17939.0053 | 17939.0053 | 7565.94 | 0 | 10373.0653 | 598815.9827 | 598815.9827 | 347176.56 | 0 | 251639.4227 | 632900.0928 | 399199.6753 | 233700.4175
Cryo1.02.01 Gen Proj OS |  | 17939.0053 | 17939.0053 | 7565.94 | 0 | 10373.0653 | 598815.9827 | 598815.9827 | 347176.56 | 0 | 251639.4227 | 632900.0928 | 399199.6753 | 233700.4175
Cryo1.02.01.01 Cryo AIP Gen Proj OS - FY13 |  | 0 | 0 | 0 | 0 | 0 | 51346.4223 | 51346.4223 | 43241.15 | 0 | 8105.2723 | 51346.4223 | 43241.15 | 8105.2723
Cryo1.02.01.02 Cryo AIP Gen Proj OS - FY14 |  | 0 | 0 | 0 | 0 | 0 | 133151.102 | 133151.102 | 75120.23 | 0 | 58030.872 | 133151.102 | 75120.23 | 58030.872
Cryo1.02.01.03 Cryo AIP Gen Proj OS - FY15 |  | 0 | 0 | 0 | 0 | 0 | 32348.8042 | 32348.8042 | 38468.63 | 0 | -6119.8258 | 32348.8042 | 38468.63 | -6119.8258
Cryo1.02.01.04 Cryo AIP Gen Proj OS - FY16 |  | 0 | 0 | 0 | 0 | 0 | 174327.2891 | 174327.2891 | 94732.98 | 0 | 79594.3091 | 174327.2891 | 94732.98 | 79594.3091
Cryo1.02.01.05 Cryo AIP Gen Proj OS - FY17 |  | 17939.0053 | 17939.0053 | 7565.94 | 0 | 10373.0653 | 133593.3311 | 133593.3311 | 64081.56 | 0 | 69511.7711 | 167677.4412 | 116104.6753 | 51572.7659
Cryo1.02.01.07 Cryo AIP Gen Proj OS - FY15 Supp |  | 0 | 0 | 0 | 0 | 0 | 74049.034 | 74049.034 | 31532.01 | 0 | 42517.024 | 74049.034 | 31532.01 | 42517.024
Cryo1.03 Cryo Basic Engineering |  | 0 | 0 | 0 | 0 | 0 | 269176.6581 | 269176.6581 | 342188.8 | 0 | -73012.1419 | 269176.6581 | 342188.8 | -73012.1419
Cryo1.03 Cryo Basic Engineering |  | 0 | 0 | 0 | 0 | 0 | 269176.6581 | 269176.6581 | 342188.8 | 0 | -73012.1419 | 269176.6581 | 342188.8 | -73012.1419
Cryo1.03 Cryo Basic Engineering |  | 0 | 0 | 0 | 0 | 0 | 269176.6581 | 269176.6581 | 342188.8 | 0 | -73012.1419 | 269176.6581 | 342188.8 | -73012.1419
Cryo1.04 Cryogenic plant sub systems |  | 0 | 0 | 530.8 | 0 | -530.8 | 3727547.1192 | 3727547.1192 | 3955836.1 | 0 | -228288.9808 | 3727547.1192 | 3955836.1 | -228288.9808
Cryo1.04.01 LN2 system |  | 0 | 0 | -0.36 | 0 | 0.36 | 413528.8731 | 413528.8731 | 331491.8 | 0 | 82037.0731 | 413528.8731 | 331491.8 | 82037.0731
Cryo1.04.01 LN2 system |  | 0 | 0 | -0.36 | 0 | 0.36 | 413528.8731 | 413528.8731 | 331491.8 | 0 | 82037.0731 | 413528.8731 | 331491.8 | 82037.0731
Cryo1.04.02 Gas management system |  | 0 | 0 | 0.35 | 0 | -0.35 | 236065.7847 | 236065.7847 | 208195.86 | 0 | 27869.9247 | 236065.7847 | 208195.86 | 27869.9247
Cryo1.04.02 Gas management system |  | 0 | 0 | 0.35 | 0 | -0.35 | 236065.7847 | 236065.7847 | 208195.86 | 0 | 27869.9247 | 236065.7847 | 208195.86 | 27869.9247
Cryo1.04.03 ODH system |  | 0 | 0 | -0.38 | 0 | 0.38 | 49757.6345 | 49757.6345 | 41355.42 | 0 | 8402.2145 | 49757.6345 | 41355.42 | 8402.2145
Cryo1.04.03 ODH system |  | 0 | 0 | -0.38 | 0 | 0.38 | 49757.6345 | 49757.6345 | 41355.42 | 0 | 8402.2145 | 49757.6345 | 41355.42 | 8402.2145
Cryo1.04.04 Cryo Refrigerator system |  | 0 | 0 | 531.77 | 0 | -531.77 | 1435657.1292 | 1435657.1292 | 1751974.32 | 0 | -316317.1908 | 1435657.1292 | 1751974.32 | -316317.1908
Cryo1.04.04 Cryo Refrigerator system |  | 0 | 0 | 531.77 | 0 | -531.77 | 1435657.1292 | 1435657.1292 | 1751974.32 | 0 | -316317.1908 | 1435657.1292 | 1751974.32 | -316317.1908
Cryo1.04.05 Cryo Compressor System |  | 0 | 0 | 0.18 | 0 | -0.18 | 426592.2083 | 426592.2083 | 417384.32 | 0 | 9207.8883 | 426592.2083 | 417384.32 | 9207.8883
Cryo1.04.05 Cryo Compressor System |  | 0 | 0 | 0.18 | 0 | -0.18 | 426592.2083 | 426592.2083 | 417384.32 | 0 | 9207.8883 | 426592.2083 | 417384.32 | 9207.8883
Cryo1.04.06 Cryo Interconnect Piping |  | 0 | 0 | -0.79 | 0 | 0.79 | 737933.9081 | 737933.9081 | 577316.39 | 0 | 160617.5181 | 737933.9081 | 577316.39 | 160617.5181
Cryo1.04.06 Cryo Interconnect Piping |  | 0 | 0 | -0.79 | 0 | 0.79 | 737933.9081 | 737933.9081 | 577316.39 | 0 | 160617.5181 | 737933.9081 | 577316.39 | 160617.5181
Cryo1.04.07 Cryo Interconnect Electrical & Controls |  | 0 | 0 | -0.43 | 0 | 0.43 | 166153.655 | 166153.655 | 281210.29 | 0 | -115056.635 | 166153.655 | 281210.29 | -115056.635
Cryo1.04.07 Cryo Interconnect Electrical & Controls |  | 0 | 0 | -0.43 | 0 | 0.43 | 166153.655 | 166153.655 | 281210.29 | 0 | -115056.635 | 166153.655 | 281210.29 | -115056.635
Cryo1.04.08 Cryogenic Fluids |  | 0 | 0 | 0.46 | 0 | -0.46 | 261857.9263 | 261857.9263 | 346907.7 | 0 | -85049.7737 | 261857.9263 | 346907.7 | -85049.7737
Cryo1.04.08 Cryogenic Fluids |  | 0 | 0 | 0.46 | 0 | -0.46 | 261857.9263 | 261857.9263 | 346907.7 | 0 | -85049.7737 | 261857.9263 | 346907.7 | -85049.7737
Cryo1.05 Experiment interfaces |  | 0 | 29319.8492 | 47694.73 | 29319.8492 | -18374.8808 | 1217212.5139 | 1184241.7675 | 1602902.81 | -32970.7464 | -418661.0425 | 1217212.5139 | 1666196.5487 | -448984.0348
Cryo1.05.01 Mu2e Interface Connection |  | 0 | 29319.8492 | 47694.73 | 29319.8492 | -18374.8808 | 1190013.5899 | 1157042.8435 | 1577736.41 | -32970.7464 | -420693.5665 | 1190013.5899 | 1641030.1487 | -451016.5588
Cryo1.05.01 Mu2e Interface Connection |  | 0 | 29319.8492 | 47694.73 | 29319.8492 | -18374.8808 | 1190013.5899 | 1157042.8435 | 1577736.41 | -32970.7464 | -420693.5665 | 1190013.5899 | 1641030.1487 | -451016.5588
Cryo1.05.02 g-2 interface connection |  | 0 | 0 | 0 | 0 | 0 | 27198.924 | 27198.924 | 25166.4 | 0 | 2032.524 | 27198.924 | 25166.4 | 2032.524
Cryo1.05.02 g-2 interface connection |  | 0 | 0 | 0 | 0 | 0 | 27198.924 | 27198.924 | 25166.4 | 0 | 2032.524 | 27198.924 | 25166.4 | 2032.524
Cryo1.06 Cryo Safety Documents |  | 0 | 0 | 0 | 0 | 0 | 155311.4174 | 155311.4174 | 125539.02 | 0 | 29772.3974 | 155311.4174 | 125539.02 | 29772.3974
Cryo1.06 Cryo Safety Documents |  | 0 | 0 | 0 | 0 | 0 | 155311.4174 | 155311.4174 | 125539.02 | 0 | 29772.3974 | 155311.4174 | 125539.02 | 29772.3974
Cryo1.06 Cryo Safety Documents |  | 0 | 0 | 0 | 0 | 0 | 155311.4174 | 155311.4174 | 125539.02 | 0 | 29772.3974 | 155311.4174 | 125539.02 | 29772.3974
Cryo1.07 Testing/Checkout |  | 33905.399 | 0 | 0 | -33905.399 | 0 | 106102.5994 | 65416.1207 | 233.53 | -40686.4787 | 65182.5907 | 133226.9186 | 69076.9556 | 64149.963
Cryo1.07 Testing/Checkout |  | 33905.399 | 0 | 0 | -33905.399 | 0 | 106102.5994 | 65416.1207 | 233.53 | -40686.4787 | 65182.5907 | 133226.9186 | 69076.9556 | 64149.963
Cryo1.07 Testing/Checkout |  | 33905.399 | 0 | 0 | -33905.399 | 0 | 106102.5994 | 65416.1207 | 233.53 | -40686.4787 | 65182.5907 | 133226.9186 | 69076.9556 | 64149.963
Cryo1.08 Cryo g-2 Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 114470.8338 | 114470.8338 | 55084.2 | 0 | 59386.6338 | 114470.8338 | 55084.2 | 59386.6338
Cryo1.08 Cryo g-2 Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 114470.8338 | 114470.8338 | 55084.2 | 0 | 59386.6338 | 114470.8338 | 55084.2 | 59386.6338
Cryo1.08 Cryo g-2 Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 114470.8338 | 114470.8338 | 55084.2 | 0 | 59386.6338 | 114470.8338 | 55084.2 | 59386.6338
Cryo1.09 Cryo Mu2e Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 94731.0013 | 0 | 0 | -94731.0013 | 0 | 94731.0013 | 95875.1233 | -1144.122
Cryo1.09 Cryo Mu2e Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 94731.0013 | 0 | 0 | -94731.0013 | 0 | 94731.0013 | 95875.1233 | -1144.122
Cryo1.09 Cryo Mu2e Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 94731.0013 | 0 | 0 | -94731.0013 | 0 | 94731.0013 | 95875.1233 | -1144.122
Cryo1.10 Cryo Distribution Box (CDB) |  | 143416.3651 | 72440.4439 | 54235.47 | -70975.9212 | 18204.9739 | 2084887.039 | 1583279.4683 | 1773503.63 | -501607.5707 | -190224.1617 | 2084887.039 | 2349173.3645 | -264286.3255
Cryo1.10 Cryo Distribution Box (CDB) |  | 143416.3651 | 72440.4439 | 54235.47 | -70975.9212 | 18204.9739 | 2084887.039 | 1583279.4683 | 1773503.63 | -501607.5707 | -190224.1617 | 2084887.039 | 2349173.3645 | -264286.3255
Cryo1.10 Cryo Distribution Box (CDB) |  | 143416.3651 | 72440.4439 | 54235.47 | -70975.9212 | 18204.9739 | 2084887.039 | 1583279.4683 | 1773503.63 | -501607.5707 | -190224.1617 | 2084887.039 | 2349173.3645 | -264286.3255
Cryo1.14 MC-1 Refrigerator Upgrades |  | 0 | 0 | 10484.99 | 0 | -10484.99 | 289199.2836 | 289199.2836 | 55330.75 | 0 | 233868.5336 | 289199.2836 | 55330.75 | 233868.5336
Cryo1.14 MC-1 Refrigerator Upgrades |  | 0 | 0 | 10484.99 | 0 | -10484.99 | 289199.2836 | 289199.2836 | 55330.75 | 0 | 233868.5336 | 289199.2836 | 55330.75 | 233868.5336
Cryo1.14 MC-1 Refrigerator Upgrades |  | 0 | 0 | 10484.99 | 0 | -10484.99 | 289199.2836 | 289199.2836 | 55330.75 | 0 | 233868.5336 | 289199.2836 | 55330.75 | 233868.5336
a. SUBTOTAL |  | 195260.7694 | 119699.2984 | 120511.93 | -75561.471 | -812.6316 | 8657454.4484 | 7987458.6513 | 8257795.4 | -669995.7971 | -270336.7487 | 8718662.8977 | 9113500.5374 | -394837.6397
b. MANAGEMENT RESERVE | [11 empty] | 826689.12
c. TOTAL |  | 195260.7694 | 119699.2984 | 120511.93 | -75561.471 | -812.6316 | 8657454.4484 | 7987458.6513 | 8257795.4 | -669995.7971 | -270336.7487 | 9545352.0177

## Template
<Header>{Report} | [7 empty] | {CostProject.Classification}
<Header>{Report} | CLASSIFICATION (When Filled In)
<Header>{Report} |  |  |  |  | CONTRACT PERFORMANCE REPORT | [13 empty] | FORM APPROVED
<Header>{Report} |  |  |  |  | FORMAT 1 - WORK BREAKDOWN STRUCTURE | [11 empty] | DOLLARS IN | {ReportSetting.ScaleCaption} | OMB No. 0704-0188
<Header>{Report} | 1. CONTRACTOR |  |  |  | 2. CONTRACT |  |  |  |  | 3. PROGRAM | [7 empty] | 4. REPORT PERIOD
<Header>{Report} | a. NAME |  |  |  | a. NAME |  |  |  |  | a. NAME | [7 empty] | a. FROM (YYYYMMDD)
<Header>{Report} | {CostProject.ContractorName} |  |  |  | {CostProject.ContractName} |  |  |  |  | {CostProject.Description}
<Header>{Report} | b. LOCATION (Address and ZIP Code) |  |  |  | b. NUMBER |  |  |  |  | b. PHASE | [7 empty] | {CostProject.PeriodStartDate}{NoCellFormat}
<Header>{Report} | {CostProject.ContractorLocation} |  |  |  | {CostProject.ContractNumber} |  |  |  |  | {CostProject.ContractPhase} | [7 empty] | b. TO (YYYYMMDD)
<Header>{Report} |  |  |  |  | c. TYPE |  |  | d. SHARE RATIO |  | c. EVMS ACCEPTANCE
<Header>{Report} |  |  |  |  | {CostProject.ContractType} |  |  | {CostProject.ShareRate} |  | {=if(CostProject.EvmsAcceptance.Id=0,"X"," ")} | NO | {=if(CostProject.EvmsAcceptance.Id=1,"X"," ")} | YES | (YYYYMMDD) | {=IF(OR(CostProject.EvmsAcceptance.Id=0,CostProject.EvmsAcceptance.Id=1), IF(CostProject.EvmsAcceptanceDate=0, " ", CostProject.EvmsAcceptanceDate), IF(CostProject.EvmsAcceptance.Id=2, "N/A"," "))}{NoCellFormat} |  |  | {CostProject.StatusDate}{NoCellFormat}
<Header>{Report} | 5. CONTRACT DATA
<Header>{Report} | a. QUANTITY | b. NEGOTIATED | c. ESTIMATED COST OF |  | d. TARGET PROFIT/FEE |  | e. TARGET PRICE |  | f. ESTIMATED PRICE |  |  | g. CONTRACT CEILING |  |  | h. ESTIMATED CONTRACT CEILING |  |  | i. DATE OF OTB/OTS (YYYYMMDD)
<Header>{Report} |  | COST | AUTHORIZED UNPRICED WORK
<Header>{Report} | {CostProject.Quantity} | {CostProject.Ctc} | {CostProject.Auw} |  | {=CostProject.Ctc*(CostProject.FeePct/100)} |  | {=CostProject.Fee+CostProject.Ctc} |  | {=CostProject.Lre+(CostProject.Cbb*(CostProject.FeePct/100))} |  |  | {CostProject.Ceiling} |  |  | {CostProject.EstCeiling} |  |  | {CostProject.OtbDate}{NoCellFormat}
<Header>{Report} | 6. ESTIMATED COST AT COMPLETION | [7 empty] | 7. AUTHORIZED CONTRACTOR REPRESENTATIVE
<Header>{Report} |  |  | MANAGEMENT ESTIMATE |  | CONTRACT BUDGET |  | VARIANCE |  | a. NAME | (Last, First, Middle Initial) |  |  |  |  | b. TITLE
<Header>{Report} |  |  | AT COMPLETION |  | BASE
<Header>{Report} |  |  | (1) |  | (2) |  | (3) |  | {CostProject.ContractRepName} | [5 empty] | {CostProject.ContractRepTitle}
<Header>{Report} | a. BEST CASE |  | {CostProject.EacBestCase} | [5 empty] | c. SIGNATURE | [8 empty] | d. DATE SIGNED | (YYYYMMDD)
<Header>{Report} | b. WORST CASE |  | {CostProject.EacWorstCase}
<Header>{Report} | c. MOST LIKELY |  | {CostProject.Lre} |  | {CostProject.Cbb} |  | {=Cell[R,C-2]-Cell[R,C-4]}
<Header>{Report} | 8. PERFORMANCE DATA
<Header>{Report} | {CriteriaN.Title}{Down}{Replace} |  | CURRENT PERIOD |  |  |  |  | CUMULATIVE TO DATE | [6 empty] | REPROGRAMMING ADJUSTMENTS |  |  | AT COMPLETION
<Header>{Report} |  |  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED COST |  | ACTUAL |  | VARIANCE | [5 empty] | BUDGETED | ESTIMATED | VARIANCE
<Header>{Report} |  |  | WORK | WORK | COST WORK |  |  | WORK | WORK | COST WORK |  |  |  |  | COST | SCHEDULE
<Header>{Report} | ITEM |  | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST | SCHEDULED | PERFORMED | PERFORMED |  | SCHEDULE |  | COST | VARIANCE | VARIANCE | BUDGET
<Header>{Report} | (1) |  | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) |  | (10) |  | (11) | (12a) | (12b) | (13) | (14) | (15) | (16)
<Header>{CriteriaN} | {=CONCATENATE(REPT(" ",CriteriaN.Level-1),"CriteriaN.Id"," CriteriaN.Description")} |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SortCodeC} | b. COST OF MONEY |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SortCodeG} | c. GENERAL AND ADMINISTRATIVE |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} | d. UNDISTRIBUTED BUDGET | [16 empty] | {CostProject.Ub} | {CostProject.EstUb} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SubTotal} | e. SUBTOTAL |  | {Column.Total} | {Column.Total} | {Column.Total} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {Column.Total} | {Column.Total} | {Column.Total} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {Column.Total} | {Column.Total} | {Column.Total} | {=Column.Total+Cell[R-1,C]} | {=Column.Total+Cell[R-1,C]} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} | f. MANAGEMENT RESERVE | [16 empty] | {CostProject.Mr}
<Footer>{Report} | g. TOTAL |  | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} |  | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C] + Cell[R-1,C]}
<Footer>{Report} | 9. RECONCILIATION TO CONTRACT BUDGET BASELINE
<Footer>{Report} | a. VARIANCE ADJUSTMENT | [10 empty] | {=Cell[R-2,C+4]} |  | {=Cell[R-2,C+1]}
<Footer>{Report} | b. TOTAL CONTRACT VARIANCE | [10 empty] | {=Cell[R-3,C]+Cell[R-1,C]} |  | {=Cell[R-3,C]+Cell[R-1,C]} |  |  |  | {CostProject.Cbb} | {CostProject.Lre} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} |  |  | (7): {CostProject.Classification}
<Footer>{Report} | CLASSIFICATION (When Filled In)
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Report Options
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Criteria: {ReportOptions.Criteria}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Calendar: {ReportOptions.CalendarSet}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Cost Sets: {ReportOptions.CostSets}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Filter: {ReportOptions.Filter}
[18 empty] | $ | % | Both
[18 empty] | Dollar | Percent | Both

## Calendar
Date | 18 Label | Hours
2017-03-31 | PREVIOUS | 17096
2017-04-30 | TODATE | 160
2024-09-30 | ATCOMPLETE | 14944

## Data
Control Account.WBS (1) | Control Account.WBS (2) | Control Account.WBS (3) | Control Account.WBS (4) | Summary Code | Cost Set | Date | Value | Currency
|  |  |  | O | Budget | 2017-03-31 | 2766016.4939 | TRUE
|  |  |  | O | Budget | 2017-04-30 | 28946.9656 | TRUE
|  |  |  | O | Budget | 2024-09-30 | 26748.4353 | TRUE
|  |  |  | O | Earned | 2017-03-31 | 2608479.817 | TRUE
|  |  |  | O | Earned | 2017-04-30 | 19844.9976 | TRUE
|  |  |  | O | Actuals | 2017-03-31 | 2830038.85 | TRUE
|  |  |  | O | Actuals | 2017-04-30 | 44439 | TRUE
|  |  |  | O | EAC | 2017-03-31 | 2830038.85 | TRUE
|  |  |  | O | EAC | 2017-04-30 | 44439 | TRUE
|  |  |  | O | EAC | 2024-09-30 | 215157.0999 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.01 |  | Budget | 2017-03-31 | 51346.4223 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.01 |  | Earned | 2017-03-31 | 51346.4223 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.01 |  | Actuals | 2017-03-31 | 43241.15 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.01 |  | EAC | 2017-03-31 | 43241.15 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.02 |  | Budget | 2017-03-31 | 133151.102 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.02 |  | Earned | 2017-03-31 | 133151.102 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.02 |  | Actuals | 2017-03-31 | 75120.23 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.02 |  | EAC | 2017-03-31 | 75120.23 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.03 |  | Budget | 2017-03-31 | 32348.8042 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.03 |  | Earned | 2017-03-31 | 32348.8042 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.03 |  | Actuals | 2017-03-31 | 38468.63 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.03 |  | EAC | 2017-03-31 | 38468.63 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.04 |  | Budget | 2017-03-31 | 174327.2891 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.04 |  | Earned | 2017-03-31 | 174327.2891 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.04 |  | Actuals | 2017-03-31 | 94732.98 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.04 |  | EAC | 2017-03-31 | 94732.98 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.05 |  | Budget | 2017-03-31 | 115654.3258 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.05 |  | Budget | 2017-04-30 | 17939.0053 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.05 |  | Budget | 2024-09-30 | 34084.1101 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.05 |  | Earned | 2017-03-31 | 115654.3258 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.05 |  | Earned | 2017-04-30 | 17939.0053 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.05 |  | Actuals | 2017-03-31 | 56515.62 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.05 |  | Actuals | 2017-04-30 | 7565.94 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.05 |  | EAC | 2017-03-31 | 56515.62 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.05 |  | EAC | 2017-04-30 | 7565.94 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.05 |  | EAC | 2024-09-30 | 52023.1153 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.07 |  | Budget | 2017-03-31 | 74049.034 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.07 |  | Earned | 2017-03-31 | 74049.034 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.07 |  | Actuals | 2017-03-31 | 31532.01 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.07 |  | EAC | 2017-03-31 | 31532.01 | TRUE
Cryo1 | Cryo1.03 | Cryo1.03 | Cryo1.03 |  | Budget | 2017-03-31 | 269176.6581 | TRUE
Cryo1 | Cryo1.03 | Cryo1.03 | Cryo1.03 |  | Earned | 2017-03-31 | 269176.6581 | TRUE
Cryo1 | Cryo1.03 | Cryo1.03 | Cryo1.03 |  | Actuals | 2017-03-31 | 342188.8 | TRUE
Cryo1 | Cryo1.03 | Cryo1.03 | Cryo1.03 |  | EAC | 2017-03-31 | 342188.8 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.01 | Cryo1.04.01 |  | Budget | 2017-03-31 | 413528.8731 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.01 | Cryo1.04.01 |  | Earned | 2017-03-31 | 413528.8731 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.01 | Cryo1.04.01 |  | Actuals | 2017-03-31 | 331492.16 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.01 | Cryo1.04.01 |  | Actuals | 2017-04-30 | -0.36 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.01 | Cryo1.04.01 |  | EAC | 2017-03-31 | 331492.16 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.01 | Cryo1.04.01 |  | EAC | 2017-04-30 | -0.36 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.02 | Cryo1.04.02 |  | Budget | 2017-03-31 | 236065.7847 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.02 | Cryo1.04.02 |  | Earned | 2017-03-31 | 236065.7847 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.02 | Cryo1.04.02 |  | Actuals | 2017-03-31 | 208195.51 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.02 | Cryo1.04.02 |  | Actuals | 2017-04-30 | 0.35 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.02 | Cryo1.04.02 |  | EAC | 2017-03-31 | 208195.51 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.02 | Cryo1.04.02 |  | EAC | 2017-04-30 | 0.35 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.03 | Cryo1.04.03 |  | Budget | 2017-03-31 | 49757.6345 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.03 | Cryo1.04.03 |  | Earned | 2017-03-31 | 49757.6345 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.03 | Cryo1.04.03 |  | Actuals | 2017-03-31 | 41355.8 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.03 | Cryo1.04.03 |  | Actuals | 2017-04-30 | -0.38 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.03 | Cryo1.04.03 |  | EAC | 2017-03-31 | 41355.8 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.03 | Cryo1.04.03 |  | EAC | 2017-04-30 | -0.38 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.04 | Cryo1.04.04 |  | Budget | 2017-03-31 | 1435657.1292 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.04 | Cryo1.04.04 |  | Earned | 2017-03-31 | 1435657.1292 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.04 | Cryo1.04.04 |  | Actuals | 2017-03-31 | 1751442.55 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.04 | Cryo1.04.04 |  | Actuals | 2017-04-30 | 531.77 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.04 | Cryo1.04.04 |  | EAC | 2017-03-31 | 1751442.55 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.04 | Cryo1.04.04 |  | EAC | 2017-04-30 | 531.77 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.05 | Cryo1.04.05 |  | Budget | 2017-03-31 | 426592.2083 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.05 | Cryo1.04.05 |  | Earned | 2017-03-31 | 426592.2083 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.05 | Cryo1.04.05 |  | Actuals | 2017-03-31 | 417384.14 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.05 | Cryo1.04.05 |  | Actuals | 2017-04-30 | 0.18 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.05 | Cryo1.04.05 |  | EAC | 2017-03-31 | 417384.14 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.05 | Cryo1.04.05 |  | EAC | 2017-04-30 | 0.18 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.06 | Cryo1.04.06 |  | Budget | 2017-03-31 | 737933.9081 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.06 | Cryo1.04.06 |  | Earned | 2017-03-31 | 737933.9081 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.06 | Cryo1.04.06 |  | Actuals | 2017-03-31 | 577317.18 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.06 | Cryo1.04.06 |  | Actuals | 2017-04-30 | -0.79 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.06 | Cryo1.04.06 |  | EAC | 2017-03-31 | 577317.18 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.06 | Cryo1.04.06 |  | EAC | 2017-04-30 | -0.79 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.07 | Cryo1.04.07 |  | Budget | 2017-03-31 | 166153.655 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.07 | Cryo1.04.07 |  | Earned | 2017-03-31 | 166153.655 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.07 | Cryo1.04.07 |  | Actuals | 2017-03-31 | 281210.72 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.07 | Cryo1.04.07 |  | Actuals | 2017-04-30 | -0.43 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.07 | Cryo1.04.07 |  | EAC | 2017-03-31 | 281210.72 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.07 | Cryo1.04.07 |  | EAC | 2017-04-30 | -0.43 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.08 | Cryo1.04.08 |  | Budget | 2017-03-31 | 261857.9263 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.08 | Cryo1.04.08 |  | Earned | 2017-03-31 | 261857.9263 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.08 | Cryo1.04.08 |  | Actuals | 2017-03-31 | 346907.24 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.08 | Cryo1.04.08 |  | Actuals | 2017-04-30 | 0.46 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.08 | Cryo1.04.08 |  | EAC | 2017-03-31 | 346907.24 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.08 | Cryo1.04.08 |  | EAC | 2017-04-30 | 0.46 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | Budget | 2017-03-31 | 1190013.5899 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | Earned | 2017-03-31 | 1127722.9943 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | Earned | 2017-04-30 | 29319.8492 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | Actuals | 2017-03-31 | 1530041.68 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | Actuals | 2017-04-30 | 47694.73 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | EAC | 2017-03-31 | 1530041.68 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | EAC | 2017-04-30 | 47694.73 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | EAC | 2024-09-30 | 63293.7387 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.02 | Cryo1.05.02 |  | Budget | 2017-03-31 | 27198.924 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.02 | Cryo1.05.02 |  | Earned | 2017-03-31 | 27198.924 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.02 | Cryo1.05.02 |  | Actuals | 2017-03-31 | 25166.4 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.02 | Cryo1.05.02 |  | EAC | 2017-03-31 | 25166.4 | TRUE
Cryo1 | Cryo1.06 | Cryo1.06 | Cryo1.06 |  | Budget | 2017-03-31 | 155311.4174 | TRUE
Cryo1 | Cryo1.06 | Cryo1.06 | Cryo1.06 |  | Earned | 2017-03-31 | 155311.4174 | TRUE
Cryo1 | Cryo1.06 | Cryo1.06 | Cryo1.06 |  | Actuals | 2017-03-31 | 125539.02 | TRUE
Cryo1 | Cryo1.06 | Cryo1.06 | Cryo1.06 |  | EAC | 2017-03-31 | 125539.02 | TRUE
Cryo1 | Cryo1.07 | Cryo1.07 | Cryo1.07 |  | Budget | 2017-03-31 | 72197.2004 | TRUE
Cryo1 | Cryo1.07 | Cryo1.07 | Cryo1.07 |  | Budget | 2017-04-30 | 33905.399 | TRUE
Cryo1 | Cryo1.07 | Cryo1.07 | Cryo1.07 |  | Budget | 2024-09-30 | 27124.3192 | TRUE
Cryo1 | Cryo1.07 | Cryo1.07 | Cryo1.07 |  | Earned | 2017-03-31 | 65416.1207 | TRUE
Cryo1 | Cryo1.07 | Cryo1.07 | Cryo1.07 |  | Actuals | 2017-03-31 | 233.53 | TRUE
Cryo1 | Cryo1.07 | Cryo1.07 | Cryo1.07 |  | EAC | 2017-03-31 | 233.53 | TRUE
Cryo1 | Cryo1.07 | Cryo1.07 | Cryo1.07 |  | EAC | 2024-09-30 | 68843.4256 | TRUE
Cryo1 | Cryo1.08 | Cryo1.08 | Cryo1.08 |  | Budget | 2017-03-31 | 114470.8338 | TRUE
Cryo1 | Cryo1.08 | Cryo1.08 | Cryo1.08 |  | Earned | 2017-03-31 | 114470.8338 | TRUE
Cryo1 | Cryo1.08 | Cryo1.08 | Cryo1.08 |  | Actuals | 2017-03-31 | 55084.2 | TRUE
Cryo1 | Cryo1.08 | Cryo1.08 | Cryo1.08 |  | EAC | 2017-03-31 | 55084.2 | TRUE
Cryo1 | Cryo1.09 | Cryo1.09 | Cryo1.09 |  | Budget | 2017-03-31 | 94731.0013 | TRUE
Cryo1 | Cryo1.09 | Cryo1.09 | Cryo1.09 |  | EAC | 2024-09-30 | 95875.1233 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | Budget | 2017-03-31 | 1941470.6739 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | Budget | 2017-04-30 | 143416.3651 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | Earned | 2017-03-31 | 1510839.0244 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | Earned | 2017-04-30 | 72440.4439 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | Actuals | 2017-03-31 | 1719268.16 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | Actuals | 2017-04-30 | 54235.47 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | EAC | 2017-03-31 | 1719268.16 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | EAC | 2017-04-30 | 54235.47 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | EAC | 2024-09-30 | 575669.7345 | TRUE
Cryo1 | Cryo1.14 | Cryo1.14 | Cryo1.14 |  | Budget | 2017-03-31 | 289199.2836 | TRUE
Cryo1 | Cryo1.14 | Cryo1.14 | Cryo1.14 |  | Earned | 2017-03-31 | 289199.2836 | TRUE
Cryo1 | Cryo1.14 | Cryo1.14 | Cryo1.14 |  | Actuals | 2017-03-31 | 44845.76 | TRUE
Cryo1 | Cryo1.14 | Cryo1.14 | Cryo1.14 |  | Actuals | 2017-04-30 | 10484.99 | TRUE
Cryo1 | Cryo1.14 | Cryo1.14 | Cryo1.14 |  | EAC | 2017-03-31 | 44845.76 | TRUE
Cryo1 | Cryo1.14 | Cryo1.14 | Cryo1.14 |  | EAC | 2017-04-30 | 10484.99 | TRUE