## Sheet1
Task Code | CTC | WP | Name | BCWS | BCWP | Schedule Variance
Cryo AIP |  |  |  | 8657454 | 7987459 | -669995
A1301.05.01 Mu2e Interface Connection | A1301.05.01 |  | Mu2e Interface Connection | 1190013.59 | 1157042.84 | -32970.75
2979 Mu2e Interface - Assemble Other Components | A1301.05.01 | 2979 | Mu2e Interface - Assemble Other Components | 323546.41 | 320310.95 | -3235.46
2980 Mu2e Interface - Assemble/Install Transfer Line | A1301.05.01 | 2980 | Mu2e Interface - Assemble/Install Transfer Line | 209679.52 | 195001.95 | -14677.57
2981 Mu2e Interface - Transfer Line Testing | A1301.05.01 | 2981 | Mu2e Interface - Transfer Line Testing | 120425.47 | 109575.43 | -10850.04
3010 Mu2e Interface - Install Helium Gas Lines between MC-1 and MC-2 | A1301.05.01 | 3010 | Mu2e Interface - Install Helium Gas Lines between MC-1 and MC-2 | 83968.56 | 79760.88 | -4207.68
A1301.07 g-2 Cryo Checkout | A1301.07 |  | g-2 Cryo Checkout | 106102.6 | 65416.12 | -40686.48
2824 Mu2e Cryo Checkout | A1301.07 | 2824 | Mu2e Cryo Checkout | 40686.48 | 0 | -40686.48
A1301.09 Cryo Mu2e Acceptance Tests | A1301.09 |  | Cryo Mu2e Acceptance Tests | 94731 | 0 | -94731
2611 Cryo Mu2e Acceptance Tests | A1301.09 | 2611 | Cryo Mu2e Acceptance Tests | 94731 | 0 | -94731
A1301.10 Cryo Distribution Box (CDB) | A1301.10 |  | Cryo Distribution Box (CDB) | 2084887.04 | 1583279.47 | -501607.57
2951 CDB received and accepted | A1301.10 | 2951 | CDB received and accepted | 133718.5 | 0 | -133718.5
2952 Acceptance tests at Fermilab | A1301.10 | 2952 | Acceptance tests at Fermilab | 12534.79 | 0 | -12534.79
2955 Fermilab Oversight of CDB | A1301.10 | 2955 | Fermilab Oversight of CDB | 129271.92 | 103458.33 | -25813.59
2963 Feedbox valves related to CDB | A1301.10 | 2963 | Feedbox valves related to CDB | 24596.76 | 0 | -24596.76
2964 Procure Transfer line A | A1301.10 | 2964 | Procure Transfer line A | 122728.87 | 106774.12 | -15954.75
2965 TLs from CDB to feedbox | A1301.10 | 2965 | TLs from CDB to feedbox | 155929.07 | 31185.81 | -124743.26
2966 TL from Helium dewar to CDB | A1301.10 | 2966 | TL from Helium dewar to CDB | 30775.09 | 6155.02 | -24620.07
2968 Procure Helium dewar | A1301.10 | 2968 | Procure Helium dewar | 61548.86 | 40006.76 | -21542.1
2997 Vendor Compl Vessel Code Stmp, Theral Shld Compnts, Trace Tube | A1301.10 | 2997 | Vendor Compl Vessel Code Stmp, Theral Shld Compnts, Trace Tube | 189454.87 | 121251.12 | -68203.75
2998 Vendor Compl Piping Spool Subassemblies | A1301.10 | 2998 | Vendor Compl Piping Spool Subassemblies | 89145.67 | 57053.23 | -32092.44
3011 Design Improvements/Upgrades | A1301.10 | 3011 | Design Improvements/Upgrades | 71150.19 | 53362.64 | -17787.55