## Sheet1
Task Code | CTC | WP | Name | BCWS | BCWP | Schedule Variance
Cryo AIP |  |  |  | 8387475 | 8048579 | -338896
A1301.02.01.10 Cryo Final Safety Documents | A1301.02.01.10 |  | Cryo Final Safety Documents | 9020.89 | 0 | -9020.89
3013 Cryo Final Safety Documents | A1301.02.01.10 | 3013 | Cryo Final Safety Documents | 9020.89 | 0 | -9020.89
A1301.05.01 Mu2e Interface Connection | A1301.05.01 |  | Mu2e Interface Connection | 1190013.59 | 1166883.02 | -23130.57
2980 Mu2e Interface - Assemble/Install Transfer Line | A1301.05.01 | 2980 | Mu2e Interface - Assemble/Install Transfer Line | 209679.52 | 199195.54 | -10483.98
2981 Mu2e Interface - Transfer Line Testing | A1301.05.01 | 2981 | Mu2e Interface - Transfer Line Testing | 120425.47 | 111986.55 | -8438.92
3010 Mu2e Interface - Install Helium Gas Lines between MC-1 and MC-2 | A1301.05.01 | 3010 | Mu2e Interface - Install Helium Gas Lines between MC-1 and MC-2 | 83968.56 | 79760.88 | -4207.68
A1301.07 Testing/Checkout | A1301.07 |  | Testing/Checkout | 72950.81 | 65416.12 | -7534.69
2824 Mu2e Cryo Checkout | A1301.07 | 2824 | Mu2e Cryo Checkout | 7534.69 | 0 | -7534.69
A1301.10 Cryo Distribution Box (CDB) | A1301.10 |  | Cryo Distribution Box (CDB) | 1914036.99 | 1614827.13 | -299209.86
2955 Fermilab Oversight of CDB | A1301.10 | 2955 | Fermilab Oversight of CDB | 129271.92 | 103458.33 | -25813.59
2965 TLs from CDB to feedbox | A1301.10 | 2965 | TLs from CDB to feedbox | 155929.07 | 46778.72 | -109150.35
2966 TL from Helium dewar to CDB | A1301.10 | 2966 | TL from Helium dewar to CDB | 30775.09 | 6155.02 | -24620.07
2968 Procure Helium dewar | A1301.10 | 2968 | Procure Helium dewar | 61548.86 | 40006.76 | -21542.1
2997 Vendor Compl Vessel Code Stmp, Theral Shld Compnts, Trace Tube | A1301.10 | 2997 | Vendor Compl Vessel Code Stmp, Theral Shld Compnts, Trace Tube | 189454.87 | 121251.12 | -68203.75
2998 Vendor Compl Piping Spool Subassemblies | A1301.10 | 2998 | Vendor Compl Piping Spool Subassemblies | 89145.67 | 57053.23 | -32092.44
3011 Design Improvements/Upgrades | A1301.10 | 3011 | Design Improvements/Upgrades | 71150.19 | 53362.64 | -17787.55