## Sheet1
Task Code | CTC | WP | Name | BCWS | BCWP | Schedule Variance
Cryo AIP |  |  |  | 8418382 | 8101573 | -316809
A1301.02.01.10 Cryo Final Safety Documents | A1301.02.01.10 |  | Cryo Final Safety Documents | 18041.78 | 0 | -18041.78
3013 Cryo Final Safety Documents | A1301.02.01.10 | 3013 | Cryo Final Safety Documents | 18041.78 | 0 | -18041.78
A1301.05.01 Mu2e Interface Connection | A1301.05.01 |  | Mu2e Interface Connection | 1190013.59 | 1173487.73 | -16525.86
2980 Mu2e Interface - Assemble/Install Transfer Line | A1301.05.01 | 2980 | Mu2e Interface - Assemble/Install Transfer Line | 209679.52 | 203389.13 | -6290.39
2981 Mu2e Interface - Transfer Line Testing | A1301.05.01 | 2981 | Mu2e Interface - Transfer Line Testing | 120425.47 | 114397.67 | -6027.8
3010 Mu2e Interface - Install Helium Gas Lines between MC-1 and MC-2 | A1301.05.01 | 3010 | Mu2e Interface - Install Helium Gas Lines between MC-1 and MC-2 | 83968.56 | 79760.88 | -4207.68
A1301.07 Testing/Checkout | A1301.07 |  | Testing/Checkout | 80485.5 | 65416.12 | -15069.38
2824 Mu2e Cryo Checkout | A1301.07 | 2824 | Mu2e Cryo Checkout | 15069.38 | 0 | -15069.38
A1301.10 Cryo Distribution Box (CDB) | A1301.10 |  | Cryo Distribution Box (CDB) | 1914036.99 | 1646864.53 | -267172.46
2955 Fermilab Oversight of CDB | A1301.10 | 2955 | Fermilab Oversight of CDB | 129271.92 | 109911.73 | -19360.19
2965 TLs from CDB to feedbox | A1301.10 | 2965 | TLs from CDB to feedbox | 155929.07 | 54575.18 | -101353.89
2966 TL from Helium dewar to CDB | A1301.10 | 2966 | TL from Helium dewar to CDB | 30775.09 | 6155.02 | -24620.07
2968 Procure Helium dewar | A1301.10 | 2968 | Procure Helium dewar | 61548.86 | 40006.76 | -21542.1
2997 Vendor Compl Vessel Code Stmp, Theral Shld Compnts, Trace Tube | A1301.10 | 2997 | Vendor Compl Vessel Code Stmp, Theral Shld Compnts, Trace Tube | 189454.87 | 121251.12 | -68203.75
2998 Vendor Compl Piping Spool Subassemblies | A1301.10 | 2998 | Vendor Compl Piping Spool Subassemblies | 89145.67 | 57053.23 | -32092.44