## Slide 1: Proton Source Task Shutdown 2014
RFQ Injection Linac
Tank 1 to 2 emmittance probe and Collimator
NTF Beam Line Repair
400 MeV Turbo Station Replacement
RIL and Linac General Maintenance
Booster Turbo Pump Replacement
Booster Vacuum Gate Valve Replacement
Booster General Maintenance

## Slide 2: RFQ Injection Line
Install isolation valve between RIL and Tank 1
Install Laser Notcher
Replace turbo pump
Replace Einzel Lens
Re-locate Einsel Lens Switch
We think this is 1 week of work but it will be ultimately driven by shop time.

## Slide 3: NTF Beam Line
A video was recently taken of the NTF Beam Line. It looks as if we understand how to dis-assemble the Beam Line and remove it. Every thing up to the 58⁰ magnet will have to be removed. Once the vacuum is disconnected at each end the beam line can be slide out of place in sections. The cables and hoses will be replaced on the way in. We think this is a 1.5 week task.

## Slide 4: 400 MeV Turbo Stations
The parts are in the manufacturing or delivery process. We anticipate having all parts in hand by the end of August. We think this is a week long task.

## Slide 5: Linac General Maintenance
Replace Stem box cover pumps from oil sealed to Scroll type.
Change oil other oil sealed vacuum pumps.
This is fill in work

## Slide 6: Booster Turbo Stations
The goal is to replace turbo pumps in quadrants of the machine. The turbo pump replacement is a couple hour task. The cable pull is two days. In each case the cable penetration has to be emptied and then re-filled. Priority should be given to turbo pump replacement in the RF sections. The cables for one quadrant, 6 turbo pumps, is 12 days. The turbo pump replacement is 3 days.

## Slide 7: Booster Vacuum Valves
Four out of seven vacuum valves are replaced.
We will continue this process until finished. Approximatey 1 day to replace and leak check each valve and vacuum system. About a week.

## Slide 8: Booster Correctors
Replace leaking corrector Long 1. Involves cutting and welding.
Replace Short 12 corrector and beam tube.
Best guess 3 days

## Slide 9: Booster General Maintenance
Leak check periods 3, 4, 5 and 6.
Support RF work as needed. Higher priority.
May have ion pumps to change.

## Slide 10: Time Concerns
Too much work for the time alloted
3.5 weeks in RIL and Linac
2.5 weeks in Booster
Any slippage will end up in week 7

## Slide 11: Thank you for your attention