## Slide 1: PIP Update
March 11th 2015

## Slide 2: Agenda
Summary Update
  Current Activities
  Updates (Joe Compton, Kiyomi Seiya)
  Additional Meetings/Notes

## Slide 3: Updates
  Linac
  SBK: Work at CPI continues – Writing up formal agreement
  LN: Received laser – During testing some damage done and so vendor is repaing
  Modulator: Buildup 54 cell modulator and testing of software continues
  Utilities: completed – task closed
    Booster
  Beam Studies:
    Cogging: Update today – but in process of making operational
    Booster optics software – No new recent studies – but Alex working on ACNET software
    Booster Longitudinal dampers – First demonstration of damping last week -
    Booster BPMs – Peter testing of board – about to place order for prototype
  RF:
    Refurbished cavity work: Cavity RF 5 verified leak on downstream end
    Cavity # 17 in test stand – testing at full gradient – to be installed next Tues/Wednesday
    New Tuners – Ferrite order released for more ferrite – asking for delivery as they are produced
    Bias Supplies: Supply # 5 has been used in testing – waiting to swap with #6
    Anode Supplies: Filling cabinet #1, Update last week by Ryan says April testing
    Perpendicular cavity: Meeting tomorrow to go over recent tests and plans for small test cavity
    Stations 20, 21 & 22: starting to ramp up activity on 20th upstairs – reviewed tunnel space
    Rework of cavities 21 & 22: Working on plan – looking at options/floor space
    New cavities: Dialogue with management still ongoing – working on design details
  Shielding: TLMs testing began yesterday with HL and about half HS correctors completed
  Transformer: Waiting for shutdown
  Absorber/Kicker: Completed for now – working on optimizing positions/reduction of losses

## Slide 4
Chart: RF Cavity Refurbishment Projections
| 40973 | 41108 | 41176 | 41226 | 41323 | 41339 | 41383 | 41410 | 41449 | 41516 | 41527 | 41568 | 41605 | 41612 | 41687 | 41722 | 41765 | 41772 | 41842 | 41872 | 41918 | 41969 | 42013 | 42051
Cavity Certified | 1 | 2 | 3 | 4 | 5 | 4 | 5 | 6 | 7 | 8 | 7 | 8 | 9 | 8 | 9 | 10 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Cavity Decertified | 1 | 2 | 3 | 4 | 5 | 4 | 5 | 6 | 7 | 8 | 7 | 8 | 9 | 8 | 9 | 10 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Cavity Recertified | 1 | 2 | 3 | 4 | 5 | 4 | 5 | 6 | 7 | 8 | 7 | 8 | 9 | 8 | 9 | 10 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Cavity Number 20 | 12
6 weeks per cavity | 17 | 18 | 19 | 20
7 weeks per cavity | 17 | 18 | 19 | 20
8 weeks per cavity | 17 | 18 | 19 | 20
9 weeks per cavity | 17 | 18 | 19 | 20
10 weeks per cavity | 17 | 18 | 19 | 20
11 weeks per cavity | 17 | 18 | 19 | 20
12 weeks per cavity | 17 | 18 | 19 | 20
Shutdown
Install

## Slide 6
7Hz 15Hz
Update Proton Flux Planning Plot
Paul Derwent

## Slide 7: Recent PIP Budget/News
FY15 Budget:
    No updates
    Need to discuss overhead rates and task updates with Ann
Update of RLS – Some Booster items remain
  Mostly cavities related
Meetings to discuss transition PIP to PIP-II continue….next meeting on Monday
DOE REVIEW of PIP
    Waiting for official document
Ann and company are going through dept. budgets
PIP PMG – Presented FY15 Q1 but did not get in laser talk (scheduled for next PMG)

## Slide 8: Upcoming Talks
Bias Supplies – Pat
15 Hz East gallery – John
Laser Notcher (pre-install update) – Dave
Salah Chaurize – Notch system operations
Keith/Tony – TLM install and operations
New Cavities(plans)
Collimator – Status and plans (V. Kapin)
Install of Cavity 21 and 22 (plans)