## Slide 1: PIP Update
March 25th 2015

## Slide 2: Agenda
Summary Update
  Current Activities
  Updates (Ken Domann, Pat Sheahan)
  Additional Meetings/Notes

## Slide 3: Updates
  Linac
  SBK: Work at CPI continues –
  LN:
  Modulator: Buildup 54 cell modulator and testing of software continues
  Utilities: completed – task closed
    Booster
  Beam Studies:
    Cogging: Continues to make operational – working on syncing to Recycler and early notch
    Booster optics software –Alex made some changes to ACNET software – need to test
    Booster Longitudinal dampers – Damping mode 50 on $19. Waiting for Alexei to return…..
    Booster BPMs – Peter testing of board -
  RF:
    Refurbished cavity work: Cavity RF 17 installed last week – back to 15 Hz cycling in east gallery
    Next cavity just finished mill work, alignment fixtures done – being put on stand for John (eow)
    New Tuners – (#2) new tuner completed and tested, # 3 almost done, #4 work just starting
    Bias Supplies: Update today – but one swapped last week – breaker issue
    Anode Supplies: Filling cabinet #1, Update last week by Ryan says April testing
    Transformer: Gear ordered and shows an expected ship date of 5/26, the spare main breaker will be here next week
    Perpendicular cavity: Measurements on mu look good – work on test cavity proceeding
    Stations 20, 21 & 22: starting to ramp up activity on 20th upstairs – reviewed tunnel space
    Rework of cavities 21 & 22: Working on plan – looking at options/floor space
    New cavities: Dialogue with management still ongoing – working on design details
  Shielding: TLMs testing continues (all Horizontals done next is verticals) Next week – ops/400KW
  Absorber/Kicker: Completed for now – working on optimizing positions/reduction of losses

## Slide 4
Shutdown
Install

## Slide 5: Recent PIP Budget/News
FY15 Budget:
    No updates
    Need to discuss overhead rates and task updates with Ann
Update of RLS – Some Booster items remain
  Mostly cavities related
Meetings to discuss transition PIP to PIP-II continue….next meeting on Monday
DOE REVIEW of PIP
    Waiting for official document
Ann and company are going through dept. budgets
PIP PMG – not scheduled

## Slide 6: Upcoming Talks
15 Hz East gallery – John
Laser Notcher (pre-install update) – Dave
Salah Chaurize – Notch system operations
Keith/Tony – TLM install and operations
New Cavities(plans)
Collimator – Status and plans (V. Kapin)
Install of Cavity 21 and 22 (plans)