Project Status
C.Y. Tan
16 July 2015

---
Status
- AL800 measurements – done
- Heating calculations and simulations – done.
  - Verification of MWS results with ACE3P (T.H. Luo, LBNL)
- Solid state driver specs – done (waiting for John Reid)
- Mock cavity – 90% machine shop work done.
  - Measurements to start once mock cavity is done.
- Anode and cathode resonators – Matt & intern
  - Drawings have started.
  - Complete and delivered 30 Sep 2015.
- Power coupler – MWS sims started. Transmission line model done.
- HOM coupler – Analytic model and Superfish model done.
  - Mock cavity will test HOM calculations – Robyn
  - Must be added to MWS model.

---
Status (cont'd)
- Solenoid for biasing – Iouri
- RF windows – Ding
  - Critical!
- Assembing the garnet disks – Kevin
  - Talk in 2 weeks to bounce ideas how this is going to be done with cooling channels.
  - Drawings of cavity (started?)
- Eddy current mitigation – Gennady
  - SSC models would be useful for us.

---
Others
- Controls
- Reviews
  - Scientific
  - Engineering
- Commissioning plan
  - High power testing