## Slide 1: PIP Update
July 22th 2015

## Slide 2: Agenda
Summary Update
  Current Activities
  Updates
    Linac Modulator Upgrade - T. Butler
    Project Schedule and Budget – K. Domann
  Additional Meetings/Notes

## Slide 3
  Linac
  SBK: Work at CPI continues – difficulties with the 4th & 5th cavities pushed the schedule one-month later
  LN: New cavity installed (07/14) -- Work continues on various fronts – Grumman amplifier, chiller, optical box, interlocks
  Modulator: Work progressing on build 28 cells modulator – all available cells tested / verified, cabinet support structures in place, installing cells (2 rows complete), CS rack assembly continues
  Booster
  Beam Studies:
    Cogging: no news
    Booster optics software: re-checking MAD file, making corrections, moving along.
    Booster Longitudinal dampers: no news
    Booster BPMs: finalizing the schematics for the timing board; FPGA code compiled and it fits in the device; modifications to Booster timing still have to be made based on the SM; layout of the timing board should begin next week, it will probably take one month to complete.
    Collimators: meeting last week – discussion to plan the next move of the secondaries. Tentative day for the move – this coming Thursday. Primaries were moved last week for demonstration.
  RF:
    Refurbished cavity:
      next cavity: getting Ion pump installed today – ready for testing by end of the week.
      next/next cavity: window welded on but not the end can assembly – either next couple of days or late next week. Also, pie-tin need to be replaced and re-machine flanges. Not likely ready for testing at least 2-3 wks.
      next/next/next cavity: not shipped yet. There are any known problems, it may be straightforward machine/fiducials.
    15 Hz: no news
    New Tuners: TD is out of ferrites! -- Ferrites boxed up & shipped to TD this morning
    Bias Supplies: last bias slowly being worked on during shutdown -- #9 is upgraded and is in the testing phase
    Anode Supplies: East in place (07.17) – expected to be up and running in 4 wks
    Transformer: Installed last weekend (07.17)
    Perpendicular bias cavity: work progressing well
    Stations 20, 21 & 22: station 20th coming along
    Rework of cavities 21 & 22: no news
    New cavities: Tom Kroc appointed as L3 manager – meeting with the team to be schedule soon – finalizing specs documentation
  Shielding: Tony presented more results at a meeting last week – there are conditions where the chipmunks will pull first – working on documentation
  Absorber/Kicker: Completed for now – working on optimizing position

## Slide 4: Recent PIP Budget/News
Budget:
  FY15 - Discussions of task updates/consolidation continues
  FY16 - M&S $$ to be uploaded this week
Update of RLS
  Replacement cavities schedule will be revised soon (T. Kroc)
  Another revision by end of CY (starting fall (?))
Meetings to discuss transition PIP to PIP-II continue
  Working on documentation
PIP PMG – Aug 6th
PIP physics workshop – tentative Oct/2015

## Slide 5: Upcoming Talks
Salah Chaurize – Notch system operations
Keith/Tony – TLM install and operations
New Cavities (plans)
Install of Cavity 21 and 22 (plans)