## Slide 1: PIP Update
August 12th 2015

## Slide 2: Agenda
Summary Update
Current Activities Update
  Ryan Crawford - Booster Anode Power Supplies
  Dave Johnson - Laser Notcher
  Valery Kapin - Booster Collimators
Additional Meetings/Notes

## Slide 3
  Linac
  SBK: Work at CPI continues – delivery likely delayed 1 month
  LN: Update today
  Modulator: Buildup continues – progressing toward 28 cell install (fiber tests, cell timing, filtering, safety review )
  Booster
  Beam Studies:
    Booster optics software: No updates
    Booster Longitudinal dampers: no news
    Booster BPMs: No update today
    Collimators: Update today
  RF:
    Refurbished cavity: (New technicians)
      Cavity #18: In test stand – running full power
        Will want to do some extra testing – thermal - next week
      Cavity #19: on mill
      Cavity #20: shipped – but work not yet started?
    15 Hz: Repairing bus bar connection/weld for stations 17 & 18 -
    New Tuners: Delivered one set – Pat made up another (for 7th tuner) – TD was given OK to pick up (John?)
      Another set of ferrites arrived – being tested
    Bias Supplies: #9 is upgraded but failed in HP testing, Next and last Bias is being worked on by EE tech (slow)
    Anode Supplies: Update today
    Transformer: Installed last weekend (07.17) - Completed
    Perpendicular bias cavity: work progressing – meeting this week to discuss mechanical layout & simulations
    Stations 20, - Preparing to hang bus bar – Next week?
    Rework of cavities 21 & 22: no news
    New cavities: Tom Kroc appointed as L3 manager – meetings – finalizing specs documentation
  Shielding: Tony and Keith – working on documentation
  Absorber/Kicker: Discussing insert removal and/or additional shielding – planning for removal later this shutdown

## Slide 4: Recent PIP Budget/News
Budget:
  FY15 - Discussions of task updates/consolidation continues
Update of RLS
  Replacement cavities schedule will be revised soon (T. Kroc)
  Another revision by end of CY (starting fall (?))
Meetings to discuss transition PIP to PIP-II continue
  Working on documentation and arranging of review as requested by Sergei/PIP-II
PIP PMG – Aug 6th went well – no real feedback
PIP physics workshop – tentative Oct/2015
AAC re-review of 700 KW plan being planned
Full AAC review in Dec

## Slide 5: Upcoming Talks
Salah Chaurize – Notch system operations
Keith/Tony – TLM install and operations
New Cavities (plans)
Cavity testing results – simulations (Reid & Hassan)
Beam Physics Workshop discussion