Project Status
C.Y. Tan
15 Oct 2015

---
Current status
- Near completion of CST model of the cavity + power coupler – Gennady
  - Check step up ratio with CST – Robyn (Looks ok)
  - Checking with transmission line model – Robyn and Tan (Looks OK)
    - There are disagreements between Mathematica and ADS, ~20% at high frequencies. Traced to small imaginary parts.
  - Checking anode input impedance of Booster fundamental cavity with COMSOL – Mohamed
  - Loadline calculations show cavity can be powered with efficiencies > 65%, PDC < 76 kW. (Looks ok)
- HOM damper CST model started – Gennady
  - Initial Smythe HOM damper model – Tan

---
Current status (cont'd)
- Solenoid for biasing garnet – Iouri
  - Changes to ramp profile affects eddy currents and design of solenoid

---
Current status (cont'd)
- Window – Ding
  - Initial selection, but requires preliminary design of cavity to continue.
- Mechanical design – Kevin
  - Have discussed with Kevin about design issues.
    - Need to get info on certain aspects of the mechanical design.
  - Received information from CERN about how they glue garnet to alumina.
    - CERN polymer lab did the gluing for them. Utilize them?

---
Add air gaps?
Comes from PAC1991_0748.pdf,
New Design Concepts for Ferrite-Tuned Low-Energy-Booster Cavities, Georg Schaffer.

---
Current status (cont'd)
- Mock cavity is being assembled – Robyn, and Tan
  - Possibility of getting a Master's student to help us with measurements.
- Received Werlatone power combiner.
  - Needs to be tested to see that it meets specs.
    - Low power test ok
    - high power test (3 kW) after startup.
- Solid state amplifier in process of being purchased
  - Bid process completed.
  - Vendor has been selected.

---
Plans
- Review!
  - In Feb 2016
  - Started working on a document of our project.
    - Will ask people to contribute to sections.