Project updates
C.Y. Tan
14 Sep 2017

---
Updates
- Cavity drawings released on 11 Sep 2017
  - Bidding has started for fabrication
- Solenoid drawings complete
  - Laser cutting of steel laminations has been sent out to vendor. Money has been obligated.
  - Slide for cavity and solenoid will be sent out soon. Not sure bidding is needed < $10k.
  - Told TD to get remaining reqs in ASAP!
- Solenoid bias supply
  - Bought
- Garnet rings
  - Shim ring – bought.
  - Remaining garnet rings – bought.
- Flat RF windows have been leak checked.
- L11 cable pulls done.
- Water
  - All parts ordered for upstairs.
  - Parts will be ordered for downstairs this week.

---
Working on ...
- Completing garnet measurements
- Complete paper study of beam loading and compensation.
- Waiting for conical windows.
- Re-test PA at 76 MHz with new cathode resonator.
- Documentation!
  - Please send me your docs so that I can update our writeup!