## Slide 1: Mechanical Update
Kevin Duel
Booster 2nd Harmonic Cavity
09 November 2017

## Slide 2: Garnet Ring Orders
Received alumina for shim pieces
  Sent to NMG
Blocks are made, machining to take place in 1-2 weeks
  Optimistically will have rings in December but more likely January
  Shim rings to be ready February at the earliest
Ordering more glue for NMG

## Slide 3: Cavity Parts Coming in and Starting Welding