## First Estimate
divide into one-time and on-going effort
System | General Assignment | Action to take | # of FE's | man-weeks One-Time | Task Duration, wks | man-weeks per year On-going | Predecessors | Deadline | Comments
VxWorks and Linux Embedded Software Tools | Voy, Diamond | Maint. of development build enviroment and version control |  |  |  | 5
Booster BPM Application Support | Diamond |  |  |  |  | 4
PIP2IT, BPM's (pre-Linux upgrade) | Slimmer | Code written by C. Briegel, supported by D. Slimmer |  |  |  | 4 |  |  | Currently at VxWorks 6.4
NML/FAST/IOTA BPM's (pre-Linux upgrade) | Slimmer | Code written by C. Briegel, supported by D. Slimmer | 2 |  |  | 4 |  |  | Currently at VxWorks 6.4
Muon Transfer Line BPM's | Diamond | Managing changes and debugging the new installation |  |  |  | 4 |  |  | Requires 10% of a programmer. Ongoing Support
MI/RR Intensity Monitors General Requests | Mc Crory | Requests for application changes and additions |  |  |  | 4
Booster Dampers | Voy | On-going support |  |  |  | 4
Booster/RR Ion Profile Monitors (IPM's) | Mc Crory, Slimmer | On-going support |  |  |  | 4
MI/RR Ion Profile Monitors (IPM's) | Mc Crory, Slimmer | On-going support | 4 |  |  | 4
MI/RR BPM's General Requests | Mc Crory, Diamond | Requests for application changes and additions | 12 |  |  | 4
Software Engineering Standards and Documentation |  | ??? |  |  |  | 4
Software Driver Support for FPGA-based Hardware |  | ??? |  |  |  | 4
Updating Labview/ACNET infrastructure | Slimmer | On-going support |  |  |  | 2
Booster BPM's | Diamond | Develop FE processes on x86 processors running Linux | 6 | 16 | 40
PIP2IT, Laser Profile Monitor (test) | Diamond | Immediate MVME 500 Vxworks 250 MHz Digitizer (Alexey) | 1 | 4 | 5 |  | Specify Reg/Mem Map | 2017-04-01 | Immediate task, needs specification meeting
PIP2IT, BPM's (Linux upgrade) | Diamond | Convert applications for x86 processors running Linux | 2 | 4.5 | 6 |  |  |  | When does this work happen ??
NML/FAST/IOTA BPM's (Linux upgrade) | Diamond | Convert applications for x86 processors running Linux | 2 | 4.5 | 6 |  |  |  | When does this work happen ??
Delivery Ring BPM's | Voy | Commissioning MVME 5500 VxWorks system |  | 4 | 48
Upgrade All VxWorks 5.4/5.5 to VxWorks 6.4 | Diamond | Go through the VxWorks upgrade on all Echotek Digitizer FE's |  | 24 | 72 |  |  | 2019-04-01 | 960 man-hours of work
RR BPM's | Mc Crory, Diamond | Reconfigure crates to utilize existing FE's fully |  | 8 | 40 |  |  |  | 500ms data collection reduced to 5ms data collection time.
MI/RR Intensity Monitors Planned Revisions (Aisha) | Mc Crory | Install new VME crates and processors and associate code |  | 4 | 48
Pixie Intensity Monitors Planned Revisions |  |  |  | 2 | 48
MI/RR Ion Profile Monitors (IPM's) | Mc Crory, Slimmer | Current Triggering Issues and High Voltage Gating |  | 4 | 48
Switchyard BPM's CW style | Mc Crory | Support for AD/Inst. 125 MHz 8-Channel Digitizers | 4 | 10 | 24
PIP II High-bandwidth DAQ R&D | Controls, Instr, RF, EES | Working group discussion and investigation |  | 4 | 48 |  |  |  | Booster BPM Upgrade used as a test case.
Linac Laser Notcher Labview | Slimmer | see Dave Johnson ???????? |  | 6 | 72
|  | TOTALS |  | 95 | 505 | 51
Instrumentation FE's previously supported by C. Breigel
NUMI BPM Front-Ends |  |  | 74.2857
Existing/Temporary VxWorks FE's at NML and CMTF |  |  | 1.5476
BLM Front-ends
Randy Thurman Keup's Projects
Electron Beam Profiler at MI-62
NML Bunch Lenth Measurement (running VxWorks 6.5)
Pixie Dump Transition Radiation Camera
IOTA Synchrotron Radiation Measurement
Note on C7: Contact Dave Slimmer
Note on C8: Contact Dave Slimmer
Note on F20: 4 man-weeks for the first. 2 man-weeks for the rest.
Note on F21: 4 man-weeks for the first. 2 man-weeks for the rest.
Note on C22: Work being done by Duanne Voy
Note on A23: 20 "duanne-style" xfer lines and pre-tev style echotek drivers 6 MI BPMs 6 RR BPMs

## Yearly Breakdown
System | General Assignment | Front-End Type | Action to take | 2018 Task Man-weeks | # of FE's | 2018 Specific Task Start Date | 2018 Specific Task End Date | Task Duration, weeks | Deadline | Predecessors
Specific Front-End Programming Tasks
Booster BPM Upgrade (Linux upgrade developed) | Diamond | Linux, x86 VME | Develop FE processes on x86 processors running Linux (Booster Devel.) | 20 | 6 | In Progress | 2018-06-01 | 40 |  | None
NML/FAST/IOTA BPM's (Linux upgrade) | Diamond | Linux, X86 VME | Convert applications for x86 processors running Linux | 4.5 | 3 | 2018-06-01 | 2018-07-15 | 6 | 2018-07-15 | Booster BPM upgrade, hardware spec
PIP2IT, BPM's (Linux upgrade) | Diamond | Linux, x86 VME | Convert applications for x86 processors running Linux | 4.5 | 2 | 2018-07-15 | 2018-09-01 | 6 |  | Booster BPM upgrade, hardware spec
PIP2IT, Laser Profile Monitor (test) | Diamond | VxWorks, PPC VME | Install new MVME 5500 Vxworks / 250 MHz Digitizer (Alexey) | 4 | 1 | 2018-02-19 | 2018-04-01 | 5 | 2018-04-01 | Specify Reg/Mem Map
PIP2IT, HWR RF Interlocks (from PIP-II BOE 121.3.10.5) | Diamond | VxWorks, PPC VME | Integrate DAE RF Interlock equipment and tie into ACNET | 25
PIP2IT, SSR1 RF Interlocks (from PIP-II BOE 121.3.10.5) | Diamond | VxWorks, PPC VME | Integrate DAE RF Interlock equipment and tie into ACNET | 20
PIP2IT Intensity Monitors Planned Revisions (Aisha) | Mc Crory | VxWorks, PPC VME | Implement revisions outlined by Aisha | 2 | 1 | TBD | TBD | 48 |  | Firmware upgrade
IOTA DCCT |  | VxWorks, PPC VME | New instance of MIBEAM (Like MI DCCT) | 2 | 1 |  |  |  |  | Decision on DAQ hardware
Delivery Ring DCCT |  | VxWorks, PPC VME | Support for latched readings and beam energy loss | 2 | 1 |  |  |  |  | Requirements from machine experts
Delivery Ring BPM's | Voy | VxWorks, PPC VME | Commissioning MVME 5500 VxWorks 5.4 system (Echotek system) | 4 | 6 | In Progress | 2018-02-01 | 48
MI/RR Intensity Monitors Planned Revisions (Aisha) | Mc Crory | VxWorks, PPC VME | Install new VME crates and processors and associated code | 4 | 6 | TBD | TBD | 48 |  | FE deployments to MI/RR, FPGA upgrade
MI/RR Ion Profile Monitors (IPM's) | Mc Crory, Slimmer | VxWorks, PPC VME | Address Current Triggering Issues and High Voltage Gating | 4 | 2 |  |  | 48
RR BPM Upgrade to Increase Data Throughput | Mc Crory, Diamond | VxWorks, PPC VME | Merge analog transition control code and DAQ code into each FE | 12 | 12 | 2018-02-01 | 2018-06-15 | 40 |  | Upgrade of RR BPM to VxWorks 6.4
Upgrade All VxWorks 5.4/5.5 to VxWorks 6.4 | Mc Crory, Diamond | VxWorks, PPC VME | VxWorks version 5.4 to 6.4 upgrade on all Echotek Digitizer FE's | 24 | 41 | TBD | 2019-12-31 | 72 | 2019-04-01 | Accelerator shutdown work
Linac Laser Notcher Labview (email from D. Johnson) | Slimmer | Labview Console | Solid State Amp modifications and Hot spare work | 10 | 1 |  |  | 72
* IOTA, PIP II, Booster need Higher speed DAQ |  |  | TOTAL = | 142
System | General Assignment | Front-End Type | Action to take | 2018 Task Man-weeks 2 Years | # of FE's | # of FE's Linux | # of FE's VxW 5.4 | # of FE's VxW 6.4 | # of FE's Labview PC
Inventory of AD/Instrumentation Front-Ends
Booster Dampers | Voy | VxWorks, PPC VME | On-going support | 8 | 1 |  | 1
Booster BPM Application Support | Diamond | Linux, x86 VME | New Application Support | 8 | 6 | 6
Booster Ion Profile Monitors (IPM's) | Mc Crory, Slimmer | VxWorks, PPC VME, Console | On-going support | 8 | 2 |  | 1 |  | 1
Linac BPM console application and OAC software | Mc Crory | OAC, Console Application | On-going support | 4 | 1 |  | 1
Linac Laser Notcher Labview | Slimmer | Labview Console | On-going support | 8 | 1 |  |  |  | 1
PIP2IT, BPM's | Slimmer | VxWorks, PPC VME | On-going support | 8 | 1 |  |  | 1
PIP2IT Intensity Monitor | Mc Crory | VxWorks, PPC VME | On-going support | 8 | 1 |  |  | 1
PIP2IT, Laser Profile Monitor | Diamond | VxWorks, PPC VME | On-going support | 8 | 1 |  |  | 1
NML/FAST/IOTA BPM's | Slimmer | VxWorks, PPC VME | On-going support | 8 | 3 |  |  | 3
NML/FASH/IOTA Intensity Monitor | Mc Crory | VxWorks, PPC VME | On-going support | 8 | 3 |  |  | 3
MI/RR BPM's | Mc Crory, Diamond | VxWorks, PPC VME | On-going support | 8 | 18 |  | 18
MI/RR Intensity Monitors | Mc Crory | VxWorks, PPC VME | On-going support | 8 | 6 |  | 3 | 3
MI/RR Ion Profile Monitors (IPM's) | Mc Crory, Slimmer | VxWorks, PPC VME, Console | On-going support | 8 | 4 |  | 2 |  | 2
MI/RR/BNB Transfer/Abort Line BPMs | Voy, Diamond | VxWorks, PPC VME | On-going support | 8 | 4 |  | 4
MI QXR | Diamond | VxWorks, PPC VME | On-going support | 8 | 1 |  | 1
Switchyard BPM's | Mc Crory | VxWorks, PPC VME | On-going support | 8 | 4 |  |  | 4
NUMI BPM Front-Ends | Voy | VxWorks, PPC VME | On-going support | 8 | 5 |  | 5
Muon Transfer Line BPM's | Diamond | VxWorks, PPC VME | On-going support | 8 | 5 |  | 5
Deliver Ring DCCT | Diamond | VxWorks, PPC VME | On-going support | 8 | 1 |  |  | 1
Delivery Ring BPM's | Voy | VxWorks, PPC VME | On-going support | 8 | 6 |  |  | 6
Existing/Temporary VxWorks FE's at NML and CMTF | Voy | VxWorks, PPC VME | On-going support | 8 | 4 |  |  | 4
BLM Front-ends | AD/CNTRLS | VxWorks, PPC VME | On-going support for/with AD/CNTRLS | 8 | 0
|  |  | TOTALS = | 172 | 78 | 6 | 41 | 27 | 4
Front-End Programming Support Tasks
VxWorks and Linux Embedded Software Tools | Voy, Diamond |  | Maint. of development build enviroment and software libraries | 5
PIP II High-bandwidth DAQ R&D | Controls, Instr, RF, EES |  | Working group discussion and investigation | 4
Software Engineering Standards and Documentation | Diamond |  | Redmine, Git, Doxygen, Software Quality Assurance manual | 4
Software Driver Support for FPGA-based Hardware | Diamond |  | Requests for software supporting AD/Inst VME modules | 4
Updating Labview/ACNET infrastructure | Slimmer |  | On-going support | 2
|  |  | TOTAL = | 19
Instrumentation FE's previously supported by C. Breigel |  |  |  | Available Programmers (per year)
NUMI BPM Front-Ends |  |  | Diamond | 1 | 1
Existing/Temporary VxWorks FE's at NML and CMTF |  |  | Mc Crory | 0.5 | 0.5
BLM Front-ends |  |  | Slimmer | 1 | 1
|  |  | * Voy | 0 | 0.5
Randy Thurman Keup's Projects |  |  |  | 2.5 | 3
Electron Beam Profiler at MI-62
NML Bunch Lenth Measurement (running VxWorks 6.5) |  |  | 2 Year Work Sum | 333 | man-weeks
Pixie Dump Transition Radiation Camera |  |  | (given a standard FTE is 1768 hours) | 7.5339 | man-years
IOTA Synchrotron Radiation Measurement
|  |  | 1 year estimate assuming uniform distribution of work | 3.767 | FTE
|  |  | Including 20% contingency on work estimation numbers | 4.5204 | FTE w/20% contingency
Note on I4: 4 man-weeks for the first. 2 man-weeks for the rest.
Note on I5: 4 man-weeks for the first. 2 man-weeks for the rest.
Note on A6: Immediate task, needs specification meeting
Note on A15: 500ms data collection reduced to 5ms data collection time.
Note on A16: 20 "duanne-style" xfer lines and pre-tev style echotek drivers 6 MI BPMs 6 RR BPMs AD/Controls has deprecated VxWorks 5.x and will end-of-line at the end of 2019