## Sheet1
Last edited: 06/24/20 | NuMI Startup Checklist
Shutdown Work
All shutdown work completed
Vacuum
All ion pumps turned on, pressures at operational values (E45)
Exercise (open and close) vacuum valves. Then verify all valves are open. (E45)
LCW Systems
MI-62 LCW system running
Horn 1 RAW skid running
Horn 2 RAW skid running
Target RAW skid running
Upstream Decay Pipe RAW skid running
Downstream Decay Pipe RAW skid running
Absorber Intermediate RAW skid running
Absorber RAW skid running
All magnets verified valved-in to LCW
All magnet power supplies verified valved-in to LCW
Check for water leaks in MI NuMI stub and NuMI pre-target enclosures
Instrumentation
Verify TLM high voltage output and Ar/CO2 gas pressure (E38 loss <16>, HV local control @ MI-65)
E:TLMHV0 readback approx. 800 V
E:TLMHVR readback approx. 800 V
E:TLMHVS setting 800 V, readback 800 V
E:TLMGP > 200 psig
BLM high voltage supplies on (local control @ MI-65)
BLM high voltage "out" and "return" parameters reading approx. 1800 V (E38 loss <4>)
Profile monitors (E41)
Sequences enabled, high voltage on, timing events verified, background seen upon trigger
Motor control fuses in place, wires put in and out of beam path to verify motion
Hadron monitor and Muon monitors 1-3
Detector gas flows approx. 30 L/hr (E38 mons <1>)
High voltage supplies on and outputting (E38 mons <2>). Local reset underground required if no output.
Sequences enabled, timing events verified, background noise plotting (E41, NuMI AAT)
Magnet power supplies
Ask MCR Crew Chief to put NuMI events in the timeline to test power supply ramps
Main power supplies
Turn on supplies in Main Injector with the I48 sequencer
Turn on supplies with the E46 sequencer
Manually turn on the NuMI CDC and critical device power supplies (D106 misc <18>)
Verify output of bend supplies (E38 bnds <3> and <4>). Reset BuLB status parameters if necessary (I18 <37>)
Verify output of quadrupole supplies (E38 quad <1>)
Correctors
Verify that corrector bulk power supplies E:CPS6NV and E:CPS65 are turned on (E38 trms <1>)
Extraction kicker
Verify that the kicker power supply I:KPS6N is on and pulsing (E38 kick <1>)
Target Hall
Horns
Turn on the opertional horn power supply E:NHSA or E:NHSB (E38 horn <1>)
Verify succesful horn pulsing, E:HSLIP approx. 45,000 A (E38 horn <2>)
Verify the horn polarity is as requested. E:HRNDIR positive for neutrinos, negative for anti-neutrinos (E38 horn <1>)
Miscellaneous |  | Ensure that the Incomplete RFGE NuMI abort input switches at MI-60 are all enabled.
Signature/Date: