## 20190123
PS Monthly Study Plan for 20190123
| Name of study | Goal | Date and Time | Beam Intensity | Studiers | Procedure | Duration (hours) | Comments | Priority scale of 1-10 (10=Highest) | Results and Comments
1 | Switch to DC mode from operational mode |  | 6:00 am-6:30 am |  | K Tripplett, S. Chaurize | Establish DC ramp | 0.5 |  | 10 | Complete
2 | Open loop Transfer Function for LLRF phase | Measure the Openloop Transfer Function for BLLRF phase | 6:30 am -10:30 noon | 2-4 Booster turns | Brian Schupbach, W. Pellico, Ed Cullerton, C. Drennan, Salah Chaurize, Kent Triplett, CY Tan,, C. Bhat |  | 4 |  | 10 | Complete
Parasitic | IPM Calibration (parasitic) | Take IPM and BPM data at the same time during this study | 6:30 am-10:30 am |  | V. Kapin and Y. Alixin |  |  | Parasitic to BLLRF study |  | IPM and PBM data were taken and off-line data analysis will follow
3 | RF phase shift/drift | Understand Phase drift in RF wave after setting frf=B:INJFRQ with balancer on and off | 10:30 am to 10:45 pm | low intensity | Cbhat, CYTan, Vgrzelak (and RF Group) | Set frf=B:INJFRQ for the frequency curve and take Vrf and WCM data. Turn off the global balancer and repeat. Two data set each. | 0.25 | May be parasitic |  | Complete Identified the problem and mitigation technique is being developed
4 | Back to Operation from DC mode |  | 10:45 am to 11:15 am |  | K Tripplett, S. Chaurize | Establish Operation | 0.5 |  | 10 | Complete
Parasitic | LLRF reboot: To help change the frf on 1-shot | Booster LLRF Reboot | 11:15 am to 12:15 noon | No beam | Brain Schupbach and Ed. Cullerton |  |  |  |  | Complete
6 | Dipole corrector scan at LEBT and orbit response study | LINAC study (No 17 in the timeline for first half hour) | 11:15 am to 12:15 noon | Low intensity | Kiyomi, and Sasha |  | 1 | Beam to LINAC beam dump | 10 | Sasha Shemuakin's 15 mins study of no Booster event in timeline messedup the Booster RF system. This is really un fortunate
We had to cancel all studies because of Booster RF problem. The cause of the problem is Sasha Shemuakin's 15 mins study of no Booster event in timeline indicated in RED earlier.
7 | Flattening the Booster ramp at injection | Flatten the Booster ramp using existing correctors (Continue the effort) | 12:15 noon to 2:pm | 2-16Booster turn | H.Pfeffer, G.Krafczyk,W. Pellico, S. Chaurize, K.Triplett,Kiyomi |  | 1.75 |  | 10 | Partially complete
[6 empty] | Total Time= | 8

## 20190220
PS Monthly Study Plan for 20190220
| Name of study | Goal | Date and Time (tentative) | Beam Intensity | Studiers | Procedure | Duration (hours) | Comments | Priority in the scale of 0-10 (10=Highest) | Results and Comments
1 | Aperture Scan around 1-Short ( Booster foil region) | Understand the aperture at injection | 6:00-7:00 am/soon after MI beam turned off |  | Kiyomi and Alex Waller, Pellico |  | 1 |  | 10 | Complete Kiyomi started at 6:00 am Did not happen because of BPM issues (completed some later period)
2 | LINAC Oil sample study | Maintainance | 7:00-8:00 am |  | LINAC Group |  | 1 |  | 10 | Complete
3 | RFQ Power scan | Scan the beam current output as a function of the RFQ power (175kW to 200kW) and quantify | 8:00-9:00 am | No beam to Booster | Kiyomi, Valeriy Kapin, Brian Schupbach |  | 1 |  | 10 | Partly Complete Kiyomi told that they took some data. To be continued
Parasitic | Swapping the RF modulator |  |  |  | RF group |  |  |  |  | Started at 7:00 am went well. Turned off E Gallary. Worked on modulator.
4 | Dipole corrector scan at LEBT and orbit response study | LINAC study (No 17 in the timeline for first half hour) | 9:00-10:00 am | No beam to Booster | Kiyomi and LINAC group |  | 1 | Beam to LINAC beam dump | 10 | This study did not happen. Instead Kiyomi decided to do Sergei's preperation study, i.e., figure out and test how to change the beam intensity of the LINAC (using movable tank-1 collimator)
Parasitic | Swapping the RF modulator |  |  |  | RF group |  |  |  |  | Continued
Back in Operational conditions
| Switch to DC mode |  |  |  | Kent and Salah |  | 0.25
5 | RF Phase drift (Cont.) | Understand the phase slip and flip for VA=VB and VA#VB in four RF cavities | 10:00 am - 2:30 pm | 3-4BT | Chandra, Tan, Victor, John |  | 3 |  | 10 | Completed. Preliminary data analysis during the study
Parasitic | Swapping the RF modulator (during RF phase drift study) |  |  |  | RF group |  |  |  |  | Complete
| Swich back to Operational mode from DC mode |  |  |  | Kent and Salah |  | 0.25 |  |  | Complete
6 | Modify the phase controller module – to remove a filter and then run some beam. |  | 2:30 pm to 3:30 pm | Beam on demand | W. Pellico, Brian Schupbach |  | 1 |  |  | DID not happen
7 | Run group A and group B out of the DDS directly. |  | 2:30 pm to 3:30 pm | Beam on demand | Brian Schupbach, Pelloci |  | 1 |  |  | Some software problem was identified and study was stopped.
8 | GMPS – Kent – needs to confirm repair to regulators. |  | 3:30 to 4:00 pm | Beam on demand | Kent and Salah |  | 0.5 | Booster should be in operational conditions to start with. | 10 | Not done. Kent told that this can be done other time.
[6 empty] | Total Time | 8

## 20190320
PS Monthly Study Plan for 20190320
| Name of study | Goal | Date and Time (tentative) | Beam Intensity | Studiers | Procedure | Duration (hours) | Comments | Priority in the scale of 0-10 (10=Highest) | Results and Comments
1 | RFQ Power scan (Continue) | Scan the beam current output as a function of the RFQ power (175kW to 200kW) and quantify | 6-8 am | No beam to Booster | Kiyomi, Valeriy Kapin, Brian Schupbach |  | 2 |  | 10 | Measurement Completed
| Go to DC mode |  | 8-8:15 am |  |  |  | 0.25 |  |  | No DC node
2 | Frequency response of the Longitudinal Damper | Commissining the damper board, and trule shooting the longitudinal damper | 8:15-10:15am | Beam on $17 | Nathan Eddy, Bill Pellico, … |  | 2 |  | 10 | Not happened
| Come back to Operational mode |  | 10:15-10:30 am |  |  |  | 0.25 |  |  | No DC node
3 | Adiabatic capture & RF Phase drift (Cont.) |  | 10:30-12 noon | Beam on $17 | Chandra, Tan, Victor |  | 1.5 |  | 5 | Did this study for 3-4 hours
4 | Modify the phase controller module – to remove a filter and then run some beam. |  | 12 noon-14:00 | Beam on demand | W. Pellico, Brian Schupbach |  | 2 |  | 10 | Did this study partly finished and completed later time
| or | [6 empty] | Studiers Choice
5 | Run group A and group B out of the DDS directly. |  |  | Beam on demand | Brian Schupbach, Pelloci |  |  |  | 10 | Studies did not happen
6 | Dipole corrector scan at LEBT and orbit response study |  | 14:00 -15:00 | No beam to Booster | Kiyomi |  | 1 | Beam to LINAC beam dump | 10 | Measurement is complete
Parasitic | Booster RF |  |  |  | Chandra, Victor? |  |  |  |  | Not done
7 | GMPS – Kent – needs to confirm repair to regulators. |  | 15:00-15:45 pm | Beam on demand | Kent and Salah |  | 0.75 | Booster should be in operational conditions to start with. | 10 | Not done
8 | Change the cogging module | Beam to RR/MI; MI should be ready | 15:45-16:00pm | Beam on demand | Kiyomi |  | 0.25 |  | 10 | Not done
[6 empty] | Total Time | 8

## 20190424
PS Monthly Study Plan for 20190424
|  | Name of study | Goal | Start Time | Duration (hours) | Beam Intensity | Studiers | Procedure | Comments | Priority in the scale of 0-10 (10=Highest) | Results and Comments
1 |  | Dipole corrector scan at LEBT and orbit response study | LINAC study (No 17 in the timeline for first half hour) | 6:00 | 1 | No beam to Booster | Kiyomi and LINAC group |  | Beam to LINAC beam dump | 10 | Done
2 |  | Foil scattering study:Measure Booster beam losses for the same number of injection turns (let's say 16), for LINAC current of 24 mA to 2 mA. | This will give us an estimate of foil-related single scattering beam losses. | 8:00 | 3 | Varying beam intensity on $17 | Sergei, Kiyomi,Jeff, Rick, Salah, Kent, John, Chandra, Tan |  |  | 10 | Done
3 | Parasetic Xe-Irrediation (STOP if it affects the studies 4 and 5) | Adiabatic capture & RF Phase drift (Cont.) |  | 11:00 | 2 | Beam on $17 | Chandra, Tan, Victor |  |  | 10 | Continued from last study
4 |  | Run group A and group B out of the DDS directly. |  | 13:00 | 2 | Beam on demand on $17 | Brian Schupbach, W.Pelloci, E. Cullerton |  |  | 10 | Needs More Time
5 |  | GMPS – Kent – needs to confirm repair to regulators. |  | 15:00 | 0.75 | Beam on demand | Kent, Salah and John |  |  | 10 | Not Done
6 |  | Flat Ramp |  |  | 2 | Beam on demand $17 | Kiyomi, Salah, Kent, John, Chandra, H.Pfeffer |  |  | Backup | Partly Completed Continued from last study

## 20190531
PS Monthly Study Plan for 20190531 (Friday) (Preliminary)
| Name of study | Parasetic Studies | Goal | Start Time | Duration (hours) | Beam Intensity | Studiers | Procedure | Priority in the scale of 0-10 (10=Highest) | Results and Comments
1 | Flat Ramp | none |  | 7:30 | 2 | Beam On demand $17 | Kiyomi |  | 10 | Partly done
2 | RF study: try to investigate if constant high Vrf makes the beam stable | none |  | 9:50 | 1 | Beam On demand $17 | Victor | Hold Vrf st much higher than operational values and see if beam is more stable as compared with operational conditions | 10 | Completed
3 | GMPS – Kent – needs to confirm repair to regulators. | none |  | 10:30 | 1 | Beam On demand $17 | Kent, Salah and John |  | 10 | Done earlier
4 | Adiabatic capture & RF Phase drift (Cont.) | none |  | 11:30 | 2 | Beam On demand $17 | Chandra, Tan, Victor |  | 10 | Did this study but not successful. However later Chandra was successful with 1-shot studies
5 | Run group A and group B out of the DDS directly. | none |  | 13:30 | 2 | Beam On demand $17 | Brian Schupbach, W.Pelloci, E. Cullerton |  | 10 | Not successful, more issues were found
6 | B121 Tune scan program- testing | none |  | 15:30 | 0.25 | Beam On demand $17 | Jeff Eldred |  | 10 | Completed
6 | See if reducing the D magnet length helps the extraction loss as compared with widining the aperture | none |  | 15:45 | 0.5 | Beam On demand $17 | Salah and Chandra |  | 10 | The finding is in-conclusive
6500000000000
12
78000000000000

## 20190626
PS Monthly Study Plan for 20190626 (Wednesday half day) (Preliminary)
| Name of study | Parasetic Studies | Goal | Start Time | Duration (hours) | Beam Intensity | Studiers | Procedure | Priority in the scale of 0-10 (10=Highest) | Results and Comments
1 | 1) Gas focusing 2) Linac tuning | none |  | 6:00 | 3 | Beam in Linac | Kiyomi |  | 10 | Complete
2 | Run group A and group B out of the DDS directly. | none |  | 9:00 | 2 | Beam On demand $17 | Brian Schupbach, W.Pelloci, E. Cullerton |  | 10 | Partly successful
3 | Adiabatic capture & RF Phase drift (Cont.) | none |  | 11:00 | 2 | Beam On demand $17 | Chandra, Tan, Victor |  | 1 | Could not identify all the problems. The efficiencies were not better than that with operation

## Summary
To be added

## 2019-All
PS Monthly Study Plan for 20190123
| Name of study | Goal | Date and Time | Beam Intensity | Studiers | Procedure | Duration (hours) | Comments | Priority scale of 1-10 (10=Highest) | Results and Comments
1 | Switch to DC mode from operational mode |  | 6:00 am-6:30 am |  | K Tripplett, S. Chaurize | Establish DC ramp | 0.5 |  | 10 | done
2 | Open loop Transfer Function for LLRF phase | Measure the Openloop Transfer Function for BLLRF phase | 6:30 am -10:30 noon | 2-4 Booster turns | Brian Schupbach, W. Pellico, Ed Cullerton, C. Drennan, Salah Chaurize, Kent Triplett, CY Tan,, C. Bhat |  | 4 |  | 10 | done
Parasitic | IPM Calibration (parasitic) | Take IPM and BPM data at the same time during this study | 6:30 am-10:30 am |  | V. Kapin and Y. Alixin |  |  | Parasitic to BLLRF study
3 | RF phase shift/drift | Understand Phase drift in RF wave after setting frf=B:INJFRQ with balancer on and off | 10:30 am to 10:45 pm | low intensity | Cbhat, CYTan, Vgrzelak (and RF Group) | Set frf=B:INJFRQ for the frequency curve and take Vrf and WCM data. Turn off the global balancer and repeat. Two data set each. | 0.25 | May be parasitic |  | Done
4 | Back to Operation from DC mode |  | 10:45 am to 11:15 am |  | K Tripplett, S. Chaurize | Establish Operation | 0.5 |  | 10 | Done
Parasitic | LLRF reboot: To help change the frf on 1-shot | Booster LLRF Reboot | 11:15 am to 12:15 noon | No beam | Brain Schupbach and Ed. Cullerton |  |  |  |  | Done
6 | Dipole corrector scan at LEBT and orbit response study | LINAC study (No 17 in the timeline for first half hour) | 11:15 am to 12:15 noon | Low intensity | Kiyomi |  | 1 | Beam to LINAC beam dump | 10 | Sasha Shemuakin's 15 mins study of no Booster event in timeline messedup the Booster RF system. This is really un fortunate
7 | Flattening the Booster ramp at injection | Flatten the Booster ramp using existing correctors (Continue the effort) | 12:15 noon to 2:pm | 2-16Booster turn | H.Pfeffer, G.Krafczyk,W. Pellico, S. Chaurize, K.Triplett,Kiyomi |  | 1.75 |  | 10
[6 empty] | Total Time= | 8
Planned Studies for future
| Scan Short 1 region (dedicated time) | Understand the aperture at injection |  | Low intensity | W. Pellico
| LLRF clean up | BLLRF clean up, Label properly, etc., |  |  | W. Pellico, Brain Schipbach, Ed. Cullerton |  | 4 | Occational intereption during operation
| Linac Collimator scan | Linac collimator study (dedicated study) |  |  | W. Pellico, Kiyomi Seiya
| Space charge tuneshift with IPM and BPM |  |  |  | Y Alixin, V Kapin and …
PS Monthly Study Plan for 20190220
| Name of study | Goal | Date and Time (tentative) | Beam Intensity | Studiers | Procedure | Duration (hours) | Comments | Priority in the scale of 0-10 (10=Highest) | Results and Comments
1 | Aperture Scan around 1-Short ( Booster foil region) | Understand the aperture at injection | 6:00-7:00 am/soon after MI beam turned off |  | Kiyomi and Alex Waller, Pellico |  | 1 |  | 10
2 | LINAC Oil sample study | Maintainance | 7:00-8:00 am |  | LINAC Group |  | 1 |  | 10
3 | RFQ Power scan | Scan the beam current output as a function of the RFQ power (175kW to 200kW) and quantify | 8:00-9:00 am | No beam to Booster | Kiyomi, Valeriy Kapin, Brian Schupbach |  | 1 |  | 10 | There is a possibility that this will be completed during the Booster RF maintainance period of 2.5hr.
Parasitic | Swapping the RF modulator |  |  |  | RF group
4 | Dipole corrector scan at LEBT and orbit response study | LINAC study (No 17 in the timeline for first half hour) | 9:00-10:00 am | No beam to Booster | Kiyomi |  | 1 | Beam to LINAC beam dump | 10 | There is a possibility that this will be completed during the Booster RF maintainance period of 2.5hr.
Parasitic | Swapping the RF modulator |  |  |  | RF group
Back in Operational conditions
| Switch to DC mode |  |  |  | Kent and Salah |  | 0.25
5 | RF Phase drift (Cont.) | Understand the phase slip and flip for VA=VB and VA#VB with four RF system | 10:00 am - 2:30 pm | 3-4BT | Chandra, Tan, Victor, John |  | 3 |  | 10
Parasitic | Swapping the RF modulator (during RF phase drift study) |  |  |  | RF group
| Swich back to Operational mode |  |  |  | Kent and Salah |  | 0.25
6 | Modify the phase controller module – to remove a filter and then run some beam. |  | 2:30 pm to 3:30 pm | Beam on demand | W. Pellico, Brian Schupbach |  | 1 |  |  | Study # 6 or 7 will take place, both need 1hr machine time each. Brian Schupbach will choose one of them
7 | Run group A and group B out of the DDS directly. |  | 2:30 pm to 3:30 pm | Beam on demand | Brian Schupbach, Pelloci |  | 1 |  |  | Study # 6 or 7 will take place, both need 1hr machine time each. Brian Schupbach will choose one of them
8 | GMPS – Kent – needs to confirm repair to regulators. |  | 3:30 to 4:00 pm | Beam on demand | Kent and Salah |  | 0.5 | Booster should be in operational conditions to start with. | 10
[6 empty] | Total Time | 8 | Study is scheduled for 8 hours. However, we have enough studies to use up all the time from 6:00am to 4:00 pm on Feb/20
| PS Monthly Study Plan for 20190320 | In progress
| Name of study | Goal | Date and Time (tentative) | Beam Intensity | Studiers | Procedure | Duration (hours) | Comments | Priority in the scale of 0-10 (10=Highest) | Results and Comments
3 | RFQ Power scan (Continue) | Scan the beam current output as a function of the RFQ power (175kW to 200kW) and quantify | 6-7 am | No beam to Booster | Kiyomi, Valeriy Kapin, Brian Schupbach |  | 1 |  | 10
4 | Dipole corrector scan at LEBT and orbit response study | LINAC study (No 17 in the timeline for first half hour) | 7-8 am | No beam to Booster | Kiyomi |  | 1 | Beam to LINAC beam dump | 10
| Go to DC mode | [5 empty] | 0.25
| Frequency response of the Longitudinal Damper |  | 8:15-10:15am |  |  |  | 2 |  | 10
| RF Phase drift (Cont.) |  | 10:15-12:15pm |  |  |  | 2 |  | 5
| Come back to Operational mode | [5 empty] | 0.25
6 | Modify the phase controller module – to remove a filter and then run some beam. |  | 12:30-14:30pm | Beam on demand | W. Pellico, Brian Schupbach |  | 2 |  | 10 | Open If Brian and Bill are not ready
7 | Run group A and group B out of the DDS directly. |  | 14:30-15:00 pm | Beam on demand | Brian Schupbach, Pelloci |  | 0.5 |  | 5 | Open If Brian and Bill are not ready
8 | GMPS – Kent – needs to confirm repair to regulators. |  | 15:00-15:45 pm | Beam on demand | Kent and Salah |  | 0.75 | Booster should be in operational conditions to start with. | 10
8 | Change the cogging module |  | 15:45-16:00pm | Beam on demand | Kiyomi |  | 0.25 |  | 10
[6 empty] | Total Time | 8 | Study is scheduled for 8 hours. However, we have enough studies to use up all the time from 6:00am to 4:00 pm on Feb/20
PS Monthly Study Plan for 20190424
|  | Name of study | Goal | Start Time | Duration (hours) | Beam Intensity | Studiers | Procedure | Comments | Priority in the scale of 0-10 (10=Highest) | Results and Comments
1 |  | Dipole corrector scan at LEBT and orbit response study | LINAC study (No 17 in the timeline for first half hour) | 6:00 | 1 | No beam to Booster | Kiyomi |  | Beam to LINAC beam dump | 10 | Done
2 |  | Measure Booster beam losses for the same number of injection turns (let's say 16), but for different linac beam currents (as low as 1-2 mA). | This will give us an estimate of foil-related single scattering beam losses. | 8:00 | 3 | Varying beam intensity on $17 | Sergei, Kiyomi,Jeff, Rick, Salah, Kent, John, Chandra, Tan |  |  | 10 | Done
3 | Parasetic Xe-Irrediation (STOP if it affects the studies 4 and 5) | Adiabatic capture & RF Phase drift (Cont.) |  | 11:00 | 2 | Beam on $17 | Chandra, Tan, Victor |  |  | 10 | Needs more time
4 |  | Run group A and group B out of the DDS directly. |  | 13:00 | 2 | Beam on demand on $17 | Brian Schupbach, W.Pelloci, E. Cullerton |  |  | 10 | Tried, but did not work. Needs more time
5 |  | GMPS – Kent – needs to confirm repair to regulators. |  | 15:00 | 0.75 | Beam on demand | Kent, Salah and John |  |  | 10 | Not Done
6 |  | Flat Ramp |  |  | 2 | Beam on demand $17 | Kiyomi, Salah, Kent, John, Chandra, H.Pfeffer |  |  | Backup | Continued from last study
Requested Studies
| Linac Collimator scan | Linac collimator study (dedicated study) |  |  | Kiyomi Seiya ,W. Pellico,
| LLRF clean up | BLLRF clean up, Label properly, etc., |  |  | W. Pellico, Brain Schipbach, Ed. Cullerton |  | 4 | Occational intereption during operation
| Space charge tuneshift with IPM and BPM |  |  |  | Y Alixin, V Kapin and …
| Measure Booster beam losses for the same number of injection turns (let's say 16), but for different linac beam currents (as low as 1-2 mA). | This will give us an estimate of foil-related single scattering beam losses. | ? | Varying beam intensity | Sergei, Kiyomi,… |  | Not known |  |  | Sasha Shemuakin's 15 mins study of no Booster event in timeline messedup the Booster RF system. This is really un fortunate
| Frequency response of the Longitudinal Damper | Commissining the damper board, and trule shooting the longitudinal damper |  | 2 | Beam on $17 | Nathan Eddy, Bill Pellico, …
| Flat Ramp |  |  | 2
| LLRF clean up | BLLRF clean up, Label properly, etc., |  | 4 |  | W. Pellico, Brain Schipbach, Ed. Cullerton
| Extractiion loss study to estabilish how short the magnets should be or how wide the magnets should be |  |  | 2 |  | Salah, Kent, John, DEJ, Chandra, W. Pellico
| Flat Ramp |  |  | 2 | Beam on demand $17 | Kiyomi, Salah, Kent, John, Chandra, H.Pfeffer |  |  | Backup | Continued from last study
| Measuring the strength of the mode-2 | Turn off mode-2 damper and look for growth rate as a function of Beam intensity
| 1) Measuring the longitudinal mode-2 strength (~2 hr) |  | done
2) Adiabatic beam capture (~2 hr)
3) Flat Ramp (eddy current corrected ramp) (~2hrs)
4) Run group A and group B out of the DDS directly
5) Extraction loss study to determine the needed length of the D-magnets
6) Foil loss, Sergie's study (?)
| 7) RF study |  |  | 1hr |  | Victor Grzelak
8) Transition crossing studies