Summary of work done
C.Y. Tan
02 Jan 2020

---
Status of PSP projects
MachineStu	Description	People	Status
Pre-Acc	Improve neutralization in LEBT with N or Xe.	Kiyomi/Dan/Pat	More beam to Tank 1
Pre-Acc	Penning source and test stand	Dan/Pat	Magnetron being modified … Revisiting arc modulator design
Pre-Acc	Laser collimation of head/tail of longitudinal beam. (LDRD)	Dave	New style flange designed for easy install/uninstall. Waiting for quote.
Pre-Acc/Linac	Simulation of PreAcc + Linac	Valeriy/Kiyomi/Dan	Permanent magnets being considered.
Pre-Acc/Linac	Re-aligned RFQ	Kiyomi/Dan/Pat	Realigned during shutdown
Linac	Klystron testing	Kiyomi	One spare tested. Now testing klystron which had a repaired water leak.
Booster	Flat injection porch	Kiyomi/Bill/George/Howie/Chris	Quick study on 11 Dec.
Booster	Adiabatic capture	Chandra/Tan	Studies done of 26 Nov.
Booster	2nd harmonic	Robyn/Tan	Repair should start this month (Jan)
Booster	Wide bore cavity	John/Robyn	In test cave being tested. Plan is to install in Booster before shutdown. Write up has been sent out to discuss the number of wide bore cavities that are really required.
Booster	2 stage collimators	Valeriy/Chandra	Meeting after Valery K. comes back from vacation (10 Jan)
Booster	Injection girder and injector civil construction to Booster	Dave/Salah/ Tan	PDR on 20 Nov
Booster	Garnet loss improvements	Robyn/Tan/Iouri/Gennady	Mechanical engineer has been assigned: Noah Curfman
Booster	Mode 2 longitudinal damper	Nathan	Victor and John did studies on 31 May to characterize mode 2 from cavity signals.
LLRF	GMPS machine learning (get rid of reference magnet)	Bill/Brian/Kiyomi	???
LLRF	Complete DDS upgrade, paraphase controller	Brian/Ed	Studies on 11 Dec. Able to get beam through transition. Delays have to be corrected. Very close to operational.
LLRF	Phase feedback, radial feedback	Brian/Ed/Bill/Tan/Valeri/Craig	Expect first test before end of May.
Beam physics projects

---
It’s the holidays so ...
Power glitch on 01 Jan 2020
BRF22 modulator died
Linac QPS303 died
KRF6 cap shorted to ground on 24 Dec. just past midnight.
Took us nearly 16 hours to find this and change it out.
Thanks to everyone who came in to fix the machine!
Kiyomi, Salah, and techs. and people who were here over the holidays who chipped in as well.

---
Task force updates
- Injection girder
  - Talked to Dan Wolf and Howie Pfeffer, we will have to do a SPICE calculation as to whether there will be an “imbalance” (transmission line modes) that will shake the beam because of the addition of 4 D magnets that are not identical to the D magnets in Booster. (30 and 31 Oct 2019)
  - Absorber review (20 Nov 2019) https://indico.fnal.gov/event/22416/
- Lattice
  - Method to reduce 1/2 integer tested.
    - Studies on 11 Dec.
    - See today’s talk.
- Digital LLRF
  - Meeting on 22 Nov
    - Ed will discuss with Bill and Kiyomi about 2nd pass of signals required for Booster from PIPII Linac
- Magnet girder tests
  - E4R has been cleaned up
  - Lead person has been identified for install/cleanup: Fernando Juarez (Mechanical)
- 20 Hz infrastructure
  - Plan to have meeting soon

---
Task force updates (cont’d)
- 2 stage collimators
  - Task code has been supplied. Drawings started.
- Tall aperture gradient extraction magnets
  - See injection girder about the problem with GMPS with non-identical D magnets.
  - Calculation for gap size first pass says about +/- 5 mm required. However, needs benchmarking with current operations.
- 20 Hz cavity tests
  - Report is being written. Status?
- 50 kV in situ cavity test. Required for PIPII
  - Plan is to test soon. 2 cavities will be chosen. Will run at 50 kV until shutdown.
- Shielding assessment
  - First meeting held. M. Vincent (Safety) will be leading.
- Tevatron tunnel mods for BTL
  - New lattice means no more rolled dipoles to get above the ceiling.
  - A beam pipe will go straight through the tunnel. Removed when necessary to move magnets.
- BTL to L11 changes
  - In BTL, a (de)buncher to rotate bunch to get smaller dp/p. Space charge increases dp/p by 2x.
  - Collimators. 2 stage? Instrumentation?