## Sheet1
Task | Working Duration | Total Duration | Responsible Party | Notes
Move PS | 8 hrs. | 3 days | Julius/Dispatch | Done in conjuction with choke
Move Choke | 8 hrs. | 3 days | Greg/Dan | Done in conjuction with PS
Move Capacitors | 8 hrs. | 2 days | Julius/Booster
Move output filter | 4 hrs. | 1 day
Terminate AC | 4 hrs. | 1 day | Ryan/Jim | Estimate assumes breaker with Lock and feeder cables is present
Install Capacitors | 16 hrs. | 3 days | Julius/Mike | Assumes some machining for copper buss
Install output filter | 4 hrs. | 4 hrs. | Julius
Ground PS | 1 hr. | 1 hr. | Ryan/Jim | Assume ground is located near supply
Ground Choke | 1 hr. | 1 hr. | Ryan/Jim
Ground Girder | 1 hr. | 1 hr. | Ryan/Jim
Ground Magnets | 1 hr. | 1 hr. | Ryan/Jim
Ground output filter | 1 hr. | 1 hr. | Ryan/Jim
Install DC cables | 4 hrs. | 4 hrs. | Ryan/Jim
Install klixons and capacitor pressure switches | 8 hrs. | 2 days | Julius
Install fence interlock to supply | 1 hr. | 1 hr. | Julius | Assume safety provides this to us and we just terminate
DC overcurrent protection | 4 hrs. | 4 hrs. | Julius
120 Vac | 8 hrs. | 8 hrs. | Jim | Only if needed for holec transducer
Install Holec Transducer | 8 hrs. | 8 hrs. | Julius
Install Stabel function generator | 2 hrs. | 2 hrs. | Julius
Inspect and Hipot | 4 hrs. | 4 hrs. | Julius/Ryan
| 96 hours | 20 days (4 weeks)
Commission supply | 40 hrs. | 5 days
Replicate Previous Readings | 40 hrs. | 20 days
| 80 hrs. | 25 days
Material money for copper and CTs?